## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui | SM/09621 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  | Junior Engineer | ORD/000253/2021-2022 | 3147/BQA | 15/12/2021 | 13/02/2022 | M/S TARUN KUMAR PATRA | 177.51 | 45.65 | 25.72 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui | SM/09621 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  | Junior Engineer | ORD/000393/2021-2022 | 204/BQA | 01/02/2022 | 02/04/2022 | M/S TARUN KUMAR PATRA | 177.51 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui | SM/09621 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000021/2021-2022 | 479/BQA | 04/03/2022 | 04/03/2022 | Resource Division | 17.36 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui | SM/09621 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joypur w/s scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. under - JJM 2020-21 fund part - A Block - Joypur , Name of OHR - Joypur . No.of Mouza :- 1 Habitations name - Panjapara, Total house hold - 62 |  |  | VCH/002401/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | NAYAN BARDHAN | 3.57 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui | SM/09621 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 |  |  | VCH/002786/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui | SM/09621 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Akui, No. of Mouza :- 04 nos. i.e. Tishanal-89, Palashi-90, Chandgram-117, Akui - 118, Total House Hold - 2822 |  |  | VCH/001172/2022-2023 | FHTC/27 | 27/09/2022 | 27/09/2022 | M/S TARUN KUMAR PATRA | 58.15 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui | SM/09621 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joypur w/s scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. under - JJM 2020-21 fund part - A Block - Joypur , Name of OHR - Joypur . No.of Mouza :- 1 Habitations name - Bamunpara, Panjapara, total house hold - 68 |  |  | VCH/002400/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | AJIT KUMAR DUTTA | 3.91 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 04 nos. mouzas (Tishanal-89, Palashi-90, Chandgram-117, Akui | SM/09621 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kushmuri Zone-A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Kushmuri, No. of Mouza :- 09 nos. i.e. Sanpura-57, Jagaldwip-58, Dasarathbati-61, Bhabapur-100, Shyampur-97, Kushmuri - 98, Khayerbani- 99, Khatnagar 101 & Jotbehar - 102, Total House Hold - 2653 |  |  | VCH/002402/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | BANDHAB ENGINEERS CO-OP SOCIETY LTD. | 126.5 | 0 | 0 | 0
Total | [13 empty] | 636.45 | 45.65 | 7.17