## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Akui Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Jhiknara-119 & Kharsi-121, Narra-120, Ratra-1 | SM/09622 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Akui Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Kharshi, No. of Mouza :- 05 nos. i.e. Jhiknara-119 & Kharsi-121, Narra-120, Ratra-122 & Salikona-123, Total House Hold - 2522 |  | Junior Engineer | ORD/000254/2021-2022 | 3148/BQA | 15/12/2021 | 13/02/2022 | TAPAS SANTRA | 175.44 | 0 | 0 | 0
Total | [13 empty] | 175.44 | 0 | 0