## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Bhagaband -1,Binodbati -2,Arjunpur - 3, | SM/09624 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000016/2021-2022 | 472/BQA | 04/03/2022 | 04/03/2022 | Resource Division | 8.81 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chuamasina Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 08 nos. mouzas (Bhagaband -1,Binodbati -2,Arjunpur - 3, | SM/09624 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chuamosina Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR -Narikala, No. of Mouza :- 08 nos. i.e.Bhagaband-1,Binodbati-2,Arjunpur-3,Nityanandapur-4,Balarampur-5,Tarajuri Gangarampur-14, Narikala-15,Karoan-16.Total House Hold - 1461 | Assistant Engineer | Junior Engineer | ORD/000418/2021-2022 | 438/BQA | 03/03/2022 | 29/03/2026 | PRINCE INDUTRIES (INDIA) | 107.14 | 0 | 0 | 80
Total | [13 empty] | 115.95 | 0 | 0