## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Jinkara-19, Srirampur-20, Pratapmath-21, | SM/09625 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kushmuri Zone-B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Gobindapur, No. of Mouza :- 10 nos. i.e. Jinkara-19, Srirampur-20, Pratapmath-21, Belbandbi-22, Kapshit-23, Paharpur-55, Fatepur-56, Baragobindapur-59, Thakurinipuskarini-60 & Karardanga-62, Total House Hold - 2610 |  | Junior Engineer | ORD/000394/2021-2022 | 205/BQA | 01/02/2022 | 02/04/2022 | M/S TARUN KUMAR PATRA | 153.87 | 43.17 | 28.06 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Jinkara-19, Srirampur-20, Pratapmath-21, | SM/09625 | Retrofitting | Supplying fabrication, Eraction on suitable RCC foundation, instalation, commissioning and testing with satisfactory completion etc. of iron Elimination plant (IEP) of capasity 100 cum 3 three months trial run at Kusmuri B OHR zone - B site in Indas block under Bankura Division, PHE Dte. |  |  | VCH/000281/2022-2023 | FHTC/26 | 26/04/2022 | 26/04/2022 | GOPAL CHANDRA CHOWDHURY | 45.75 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Jinkara-19, Srirampur-20, Pratapmath-21, | SM/09625 | Retrofitting | Shifting of UPVC pipe line due to widening of Kotulpur Indas PWD road under Kushmuri Zone -B (Indas BRGF) water supply scheme under Bishnupur Sub-Division of Bankura Division, PHE Dte.(Part A) (Sl. No. 06) |  | Junior Engineer | ORD/000563/2021-2022 | 40/VSD | 22/02/2022 | 24/03/2022 | OSMAN SEKH | 4.52 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Jinkara-19, Srirampur-20, Pratapmath-21, | SM/09625 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000024/2021-2022 | 480/BQA | 04/03/2022 | 04/03/2022 | Resource Division | 16.05 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Kushmuri Zone-B (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 10 nos. mouzas (Jinkara-19, Srirampur-20, Pratapmath-21, | SM/09625 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kushmuri Zone-B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Gobindapur, No. of Mouza :- 10 nos. i.e. Jinkara-19, Srirampur-20, Pratapmath-21, Belbandbi-22, Kapshit-23, Paharpur-55, Fatepur-56, Baragobindapur-59, Thakurinipuskarini-60 & Karardanga-62, Total House Hold - 2610 |  |  | VCH/001546/2022-2023 | FHTC/06 | 06/01/2023 | 06/01/2023 | M/S TARUN KUMAR PATRA | 93.05 | 0 | 0 | 0
Total | [13 empty] | 313.24 | 43.17 | 13.78