## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Laying extra HDPE pipeline to cover Kulmura, Radhanagar & moukura mouza for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Arjunpur Zone-N under Bankura - l - ll & Barjora block water Supply Scheme (BRGF Ph-I) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002783/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | SUBHADIP KOLEY | 4.4 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-C) , Total House Hold -172 |  |  | VCH/002434/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | ASHOKE KUMAR DEY | 1.78 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhelai Diha (81) & Jagatpur (82) mouzas by retrofitting Zone-E (Naria) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002781/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | KOUSIK MONDAL | 2.65 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 01 ( Panchbaga.), Total House Hold - 438 |  |  | VCH/002422/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | GOUTAM BHOWMIK | 11.27 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 10 nos. i.e. Gangabati-32, Maurui-33, Bhagabanbati-34, Nunduri-35, Bajitpur-36, Bangalchwak-37, Keneti-50, Panchkona-51, Amrul-52 & Abdulpur-53, Total House Hold - 2627 |  |  | VCH/002441/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | KHAN ENTERPRISE | 145.4 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhaban zone - A under Saltora - Chhatna block w/s scheme ( BRGF ph - l project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna , Name of OHR - Dhaban . No.of Mouza :-01 Bhelani ), Total House Hold - 140 , |  |  | VCH/002410/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | TAPAS KUMBHAKAR | 1.96 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 Shitla (PART-C) & PabayaTotal House Hold -119 |  |  | VCH/002414/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | ASHOKE KUMAR DEY | 0.88 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Estimate for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Murku (210) mouza by retrofitting of Piped Water Supply Scheme for Phulberia & Its Adjoining Mouzas at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002435/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | SWAPAN KUMAR UPADHYAY | 7.22 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Bagapatal (Part), Total House Hold- 71 (Sl No of Work- 03) |  |  | VCH/002406/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | PRADIP CHAKRABORTY | 1.1 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Bishnupur, Name of OHR - Prakash, No. of Mouza :- 09 nos. i.e. Narayanpur-70, Uliara-71 & Tenera-80, Mahishkhoar-67, Ramnagar-68, Prakash-69, Katna-79, Basantapur-81 & Dihar-82, Total House Hold - 2326 |  |  | VCH/000204/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | SIB SANKAR CHOWDHURY | 85.33 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Bagapatal (Part), Total House Hold- 72 (Sl No of Work- 04) |  |  | VCH/002407/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | PRADIP CHAKRABORTY | 0.03 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Laying Extra UPVC Pipe Line to Cover PANCHBAGA 'mouza for construction and commissioning ofF 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HORIALGORA (Zone- O) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002427/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | GOUTAM BHOWMIK | 4.38 | 0 | 0 | 0
13 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Rectro fitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of pipe water supply scheme of Monipur (ZONE- D ) W/S Scheme and its adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Saltora, Name of OHR:- Manipur, No.of Mouza :- 14 nos, (Alunia, Damodarpur, Monipur, Khagra, Sukhabad , Katabaid, Demramol, Beriatha, Janadudumar Rampur Raghumathpur, l, Chhatpathor, Shalroha, Nimra,) Total House Hold - 2711. |  |  | VCH/002403/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | SIB SANKAR CHOWDHURY | 76 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 02 nos Sonareka (Part) & Sitaldihi, Total House Hold- 61 (Sl No of Work- 12) |  |  | VCH/002409/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | M/S NAYAN BARDHAN | 0.54 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joypur w/s scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. under - JJM 2020-21 fund part - A Block - Joypur , Name of OHR - Joypur . No.of Mouza :- 1 Habitations name - Loharpara Total house hold - 35 |  |  | VCH/002404/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | BIT ENTERPRISE | 2.99 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. si no -02 |  |  | VCH/002424/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | BISWESWAR CONSTRUCTION | 4.64 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 01, Magra(PART-I )Total House Hold - 139.' |  |  | VCH/002405/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | SK. SAHAJAHAN | 1.19 | 0 | 0 | 0
18 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | "extra HDPE pipe line of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no -03" |  |  | VCH/002425/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | BISWESWAR CONSTRUCTION | 2.32 | 0 | 0 | 0
19 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Laying Extra UPVC pipe Line to Cover Bagatapole mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002431/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | ASHIS PAL | 4.9 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- ChandarBardgan Para (Part- A), Total House Hold -50. |  |  | VCH/002421/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | MAYA CONSTRUCTION | 0.32 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Laying Extra UPVC pipe Line to Cover Vangahira mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte |  |  | VCH/002430/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | TARINI CHARAN UPADHYAY | 4.19 | 0 | 0 | 0
22 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Laying Extra UPVC pipe Line to Cover Vangahira mouza for construction and commissioning of'' 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/002433/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | TAPAN KUMAR UPADHYAY | 4.88 | 0 | 0 | 0
23 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of MALIARA (Zone - A) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - MALIARA (Zone - A) . No.of Mouza :- Maliara part-II(Part-D) , Total House Hold -173 |  |  | VCH/002429/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | GOUTAM GHOSH | 1.09 | 0 | 0 | 0
24 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Rectrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KOTALPUKUR (Zone - B) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KOTALPUKUR (Zone - B)) . No.of Mouza :-01 (Rajprasadpur (Part), Total House Hold -473 |  |  | VCH/002437/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | RANABIR CHATTERJEE | 2.02 | 0 | 0 | 0
25 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No. of Mouza :- 01 Laxmi janardanpu (Part) Total House Hold- 70 (Sl No of Work- 07) |  |  | VCH/002408/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | ZAKIR HOSSAIN MONDAL | 0.49 | 0 | 0 | 0
26 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of FHTC (Functional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Kanchanpur (Zone - C) W/S Scheme under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph- I project) under Bankura Sadar Sub- Division of Bankura Division, PHE Dte Block - Barjora, No.of Mouza :- 01 Shitla part - B . Total House Hold - 119 nos. |  |  | VCH/002413/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | SANDHYA DEY | 0.96 | 0 | 0 | 0
27 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Bankati (Zone - R) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura - Il , Name of OHR - Bankati . No.of Mouza :- 02 Bankati & Beldanga Total House Hold -132 |  |  | VCH/002415/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | SHYAMAL KUMAR DAS | 1.16 | 0 | 0 | 0
28 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Rol Zone - B W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Birasimul, No. of Mouza :- 4 nos. i.e. Birasimul-70, Shakrul-71, Suripuskarini-72 & Dhamur-73, Total House Hold - 1343 |  |  | VCH/002786/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | M/S TARUN KUMAR PATRA | 71.95 | 0 | 0 | 0
29 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of HARIALGORA (Zone - O) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- I & II, Name of OHR - Harialgara. No.of Mouza :- 03 (Badra,Gopalpur, Bhedua(Part), Total House Hold - 435' |  |  | VCH/002411/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | GOUTAM BHOWMIK | 4.3 | 0 | 0 | 0
30 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SONADAHA (Zone - Q) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph- I project) under Bankura Sadar Sub- Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Sonadaha, No.of Mouza :- 02 Parasiabad & LAXMI JANARDANPUR (Part), Total House Hold- 67 (Sl No of Work- 01), |  |  | VCH/002412/2021-2022 | FHTC/21 | 21/02/2022 | 21/02/2022 | M/S NAYAN BARDHAN | 0.76 | 0 | 0 | 0
31 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHATARKANALI (Zone - L) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Bankura- II, Name of OHR - Chatarkanali, No.of Mouza :- 04 nos, (Talandanga, Upar Narrah, Chhatarkanali, Rampur, ), Total House Hold - 530.' |  |  | VCH/002779/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | M/S TARUN KUMAR PATRA | 5.53 | 0 | 0 | 0
32 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of FHTC (Funtional House Hold Tap Connection in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of KANCHANPUR (Zone - C) under Bankura - I,II Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora , Name of OHR - KANCHANPUR (Zone - C) . No.of Mouza :- 01 , Khandari ( PART-B) , Total House Hold -130 ( Sl .No.- 02 ) |  |  | VCH/002784/2021-2022 | FHTC/4 | 04/03/2022 | 04/03/2022 | BIJOY KOLEY | 1.18 | 0 | 0 | 0
33 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYTUNGA (Zone - H)) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora & Bankura- II, Name of OHR - JOYTUNGA (Zone - H) . No.of Mouza :- 01, Kolaberia (PART- A), Total House Hold -427 |  |  | VCH/002438/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | UNIVERSAL CONSTRUCTION | 8.89 | 0 | 0 | 0
34 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Prakash Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte.Block - Bishnupur, Name of OHR - Prakash, No. of Mouza :- 09 nos. i.e. Narayanpur-70, Uliara-71 & Tenera-80, Mahishkhoar-67, Ramnagar-68, Prakash-69, Katna-79, Basantapur-81 & Dihar-82, Total House Hold - 2326 |  | Junior Engineer | ORD/000304/2021-2022 | 3351/BQA | 30/12/2021 | 28/02/2022 | SIB SANKAR CHOWDHURY | 179.18 | 0 | 0 | 0
35 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Prakash Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 09 nos. mouzas (Narayanpur-70, Uliara-71 & Tenera-80, Mahi | SM/09626 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 476/BQA | 04/03/2022 | 04/03/2022 | Resource Division | 12.79 | 0 | 0 | 0
Total | [13 empty] | 658.64 | 0 | 0