## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Karisunda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Simulia-46, Bagmari-47, Santara-48, Rasulpur-49 | SM/09627 | Retrofitting | Continuation work order for Hiring vehicle for office use of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. for 06 (six) months from 01.02.2022 to 31.07.2022 |  | Junior Engineer | ORD/000720/2021-2022 | 12/VSD | 27/01/2022 | 27/07/2022 | SWAPAN KUMAR BIT | 0.86 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Karisunda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Simulia-46, Bagmari-47, Santara-48, Rasulpur-49 | SM/09627 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 31/03/2023 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer |  | ORD/000881/2022-2023 | 37/A/VSD | 27/02/2023 | 27/03/2023 | TAPAN KUMAR UPADHYAY | 0.29 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Karisunda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Simulia-46, Bagmari-47, Santara-48, Rasulpur-49 | SM/09627 | Retrofitting | Hiring vehicle for office of the Assistant Engineer, Bishnupur Sub-Division under Bankura Division P.H.E. Dte. as & when required upto 28/02/2023 for supervision of work and identification of land in connection with 4 nos. uncovered blocks within Bishnupur Sub-Division. | Assistant Engineer |  | ORD/001030/2021-2022 | 11/A/VSD | 30/01/2022 | 28/02/2022 | TAPAN KUMAR UPADHYAY | 0.23 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Karisunda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Simulia-46, Bagmari-47, Santara-48, Rasulpur-49 | SM/09627 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000012/2022-2023 | 2036/BQA | 29/09/2022 | 29/09/2022 | Resource Division | 14.29 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Karisunda (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 16 nos. mouzas (Simulia-46, Bagmari-47, Santara-48, Rasulpur-49 | SM/09627 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Karisunda W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Simulia, No. of Mouza :- 16 nos. i.e. Simulia-46, Bagmari-47, Santara-48, Rasulpur-49, Kapshit-23, Belbadbi-22, Bishnubati-25, Paschim Srirampur-38, Patraganti-39, Kalagram-40, Sahisnara-41, Pantrai-42, Tentulmuri-43, Chandpur-44, Singerbandh-45 & Karisunda-54, Total House Hold - 3761 | Assistant Engineer | Junior Engineer | ORD/000076/2022-2023 | 1808/BQA | 22/08/2022 | 21/10/2022 | SIB SANKAR CHOWDHURY | 250.69 | 0 | 0 | 85
Total | [13 empty] | 266.37 | 0 | 0