## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | SM/09629 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Lakshmanpur, No. of Mouza :- 17 nos, (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathanbera, Danmari, Kadra, Nisehintapur, Laxmanpur, Shunri Chitra, Lari, Nuniadihi, Panjanpahari, Sarenga Phulberia, Jagannathpur Total House Hold - 1984 nos. |  | Junior Engineer | ORD/000307/2021-2022 | 3372/BQA | 31/12/2021 | 01/03/2022 | SWAPAN KUMAR UPADHYAY | 100.48 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | SM/09629 | Retrofitting | Laying extra HDPE Pipe Line to Cover Saparda, Tisra, Nuniadihi, Lorri mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000232/2022-2023 | 1312/BQA | 15/06/2022 | 30/06/2022 | SUMITA UPADHYAY | 4.56 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | SM/09629 | Retrofitting | Laying extra HDPE Pipe Line to Cover Lorri mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000233/2022-2023 | 1311/BQA | 15/06/2022 | 30/06/2022 | SUMITA UPADHYAY | 4.88 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | SM/09629 | Retrofitting | Laying extra HDPE Pipe Line from Banpusra to Kalaibad to increase pressure in Kalaibad mouza for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000161/2022-2023 | 1322/BQA | 15/06/2022 | 30/06/2022 | ASHOKE KUMAR DEY | 4.66 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | SM/09629 | Retrofitting | laying extra HDPE Pipe Line to Cover Danmari mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000231/2022-2023 | 1307/BQA | 15/06/2022 | 30/06/2022 | SUMITA UPADHYAY | 4.23 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | SM/09629 | Retrofitting | Laying of UPVC pipe line from Surichitra to Nuniadihi & Panjongora due to damage by PMGSY Road of LAKSHMANPUR (ZONE- L) under Saltora- Chhatna Block W/S Scheme (BRGF Ph - I project)under Bankura Sadar Sub-Division, of Bankura Division, P.H.E. Dte. Saltora Water Supply Scheme under Bankura Sadar Sub-Division, of Bankura Division, P.H.E. Dte. (Under JJM / Jal Swapna Fund) |  | Junior Engineer | ORD/000608/2021-2022 | 887/BSD | 08/09/2021 | 23/09/2021 | MAA USHA CONSTRUCTION | 3.77 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | SM/09629 | Retrofitting | Laying extra HDPE Pipe Line to Cover Panjanpahari mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000230/2022-2023 | 1327/BQA | 15/06/2022 | 30/06/2022 | SUMITA UPADHYAY | 2.98 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | SM/09629 | Retrofitting | Laying extra HDPE Pipe Line from Kalaibad to Tisra to increase pressure in Tisra mouza for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000460/2022-2023 | 1323/BQA | 15/06/2022 | 30/06/2022 | GOURANGA CHATTERJEE | 4.46 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 17 Nos. Mouzas (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathan | SM/09629 | Retrofitting | Survey work for Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Lakshmanpur, No.of Mouza :- 17 nos, (Radhanagar, Banspura, Kelaibad, Bhimpur, Tishra, Saparda, Pathanbera, Danmari, Kadra, (Nisehintapur, Laxmanpur, Shunri Chitra, Lari, Nuniadihi, Panjanpahari, Sarenga Phulberia, Jagannathpur) Total House Hold - 1984 nos. |  | Junior Engineer | ORD/000877/2021-2022 | 73/BSD | 14/01/2022 | 14/04/2022 | TAPAS DEY | 0.66 | 0 | 0 | 0
Total | [13 empty] | 130.68 | 0 | 0