## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) | SM/09630 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Bloc k of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Lakshmanpur, No. of Mouza :- 7 nos, (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Bansura, Naoadihi) Total House Hold - 1960 nos. |  | Junior Engineer | ORD/000247/2021-2022 | 3360/BQA | 31/12/2021 | 01/03/2022 | PARAMESWAR CHOWDHURY | 90.29 | 90.23 | 99.93 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) | SM/09630 | Retrofitting | Laying Extra HDPE Pipe Line to Cover Gholgora, Naoadihi mouza for retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block of Saltora- Chhatna W/S Scheme (BRGF ph - I project) under Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000966/2022-2023 | 341/KSD | 16/08/2022 | 05/09/2022 | PARAMESWAR CHOWDHURY | 3.97 | 3.84 | 96.73 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) | SM/09630 | Retrofitting | Construction of S.S.P including laying of P.V.C extension pipe Line at Tegori Hari Mandir to Namapara & Golgora Bouripara of Chhatna block under Saltora -Chhatna W/S Scheme under BQA (HQ) of Bankura Division P.H.E. Dte. |  | Junior Engineer | ORD/000625/2021-2022 | 691/BSD | 11/06/2021 | 26/06/2021 | SIB SANKAR CHOWDHURY | 4.91 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) | SM/09630 | Retrofitting | Survey work for Retrofitting works for creacion of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) under Chhatna Block Saltora- Chhatn W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR - Lakshmanpur, No.of Mouza :- 07 nos, (Gholgora, Teghori, Bagjuri,Dardali, Kendsaer, Niasa Naoadihi), Total House Hold - 1960 nos. |  | Junior Engineer | ORD/000876/2021-2022 | 74/BSD | 14/01/2022 | 14/04/2022 | TAPAS DEY | 0.65 | 0.6 | 91.38 | 99
5 | BANKURA |  | Bankura Division | Construction & commissioning of Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for 07 Nos. Mouzas (Gholgora, Teghori, Bagjuri, Dardali, Kendsaer, Naise, Naoadihi) | SM/09630 | Retrofitting | Laying of HDPE Pipe Line from Jagannath more to Tegori & Bankura-Purulia main road (NH-60) to Gholgora to increase water pressure at Gholgora, Teghori mouza of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Laxmanpur (Zone - L) of Chhatna Block under Saltora - Chhatna W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000145/2023-2024 | 1338/BQA | 01/06/2023 | 01/04/2025 | SUNIL KUMAR MANDAL | 8.49 | 0 | 0 | 5
Total | [13 empty] | 108.32 | 94.67 | 87.4