## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-A) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Bl | SM/09633 | Retrofitting | Supply of VALVE including loading, unloading, stacking etc. all comlete for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-A)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) |  | Junior Engineer | ORD/000189/2022-2023 | 349/BSD | 12/04/2022 | 27/04/2022 | SSPR VALVE MANUFACTURING PVT. LTD. | 4.98 | 4.98 | 100 | 0
2 | BANKURA |  | Bankura Division | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-A) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Bl | SM/09633 | Retrofitting | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part- A & B)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II) Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-II), No. of Mouza :-01 no, Barjora, Total House Hold -3307 nos. |  | Junior Engineer | ORD/000021/2022-2023 | 1063/BQA | 10/05/2022 | 09/07/2022 | GOPAL CHANDRA CHOWDHURY | 367.48 | 179.25 | 48.78 | 0
3 | BANKURA |  | Bankura Division | New pipe line with Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-A) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Bl | SM/09633 | Retrofitting | Survey work for Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of 01 nos. Mouza ( Barjora (Part-A)) of BARJORA Water Supply Scheme(Left out mouzas of Barjora Block under B.R.G.F Phase -I) within Barjora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Zone-II). Block -Barjora, Name of OHR - LEFT OUT MOUZAS OF BARJORA BLOCK UNDER BRGF PHASE-I (ZONE-II), No. of Mouza :-01 no., (Barjora (Part-A)), Total House Hold -1657 nos. |  | Junior Engineer | ORD/000880/2021-2022 | 82/BSD | 14/01/2022 | 14/04/2022 | TAPAS DEY | 0.55 | 0.55 | 100 | 0
Total | [13 empty] | 373.02 | 184.79 | 49.54