## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Baramara-149 & Kulaijuri-134) of CHAK | SM/09638 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuparsole Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 2 nos. i.e. Baramara-149 & kulaijuri-134 , Total House Hold -793 |  | Junior Engineer | ORD/000193/2021-2022 | 3026/BQA | 29/11/2021 | 29/12/2021 | UNIVERSAL CONSTRUCTION | 70.43 | 60.62 | 86.07 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Chakuparsole Zone-A (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos. mouzas (Baramara-149 & Kulaijuri-134) of CHAK | SM/09638 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Chakuporsol Zone- A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Majuria, No. of Mouza :- 08 nos. i.e. Dhabani- 136, Chitrang-137,Baliguma-138, Indkuri-139,Taldangra-140,Domberya-141,Majdiha-142 and Hetagara-143 Total house hold - 799 ( Out of 949) |  | Junior Engineer | ORD/000195/2021-2022 | 3029/BQA | 29/11/2021 | 29/12/2021 | SUMITA UPADHYAY | 61.96 | 0 | 0 | 0
Total | [13 empty] | 132.39 | 60.62 | 45.79