## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its | SM/09639 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000105/2021-2022 | 2501/BQA | 23/09/2021 | 23/10/2021 | GOUTAM BHATTACHRYYA | 52.99 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its | SM/09639 | Retrofitting | Work Order for Household survey in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas under Parsola, Zone-A to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 17) | Assistant Engineer | Junior Engineer | ORD/000604/2021-2022 | 803/KSD | 14/12/2021 | 14/03/2022 | TAPAS DEY | 0.3 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its | SM/09639 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Amrul Zone - A W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Amrul, No. of Mouza :- 10 nos. i.e. Gangabati-32, Maurui-33, Bhagabanbati-34, Nunduri-35, Bajitpur-36, Bangalchwak-37, Keneti-50, Panchkona-51, Amrul-52 & Abdulpur-53, Total House Hold - 2627 |  |  | VCH/002441/2021-2022 | FHTC/18 | 18/02/2022 | 18/02/2022 | KHAN ENTERPRISE | 145.4 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its | SM/09639 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/000209/2022-2023 | FHTC/11 | 11/04/2022 | 11/04/2022 | GOUTAM BHATTACHRYYA | 32.23 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its | SM/09639 | Retrofitting | Laying extra HDPE pipe lineto cover Rudra (38 ) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 01 |  |  | VCH/002838/2021-2022 | FHTC/9 | 09/03/2022 | 09/03/2022 | GOPAL CHANDRA CHOWDHURY | 4.49 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its | SM/09639 | Retrofitting | laying extra UPVC pipe line to cover Pukhuria (10) mouzas Construction and commissioning of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of retrofitting Parsola Zone - B under and its adjoining mouza under Simlapal water supply shceme under BRGF (Phase - I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, |  |  | VCH/003125/2021-2022 | FHTC/30 | 30/03/2022 | 30/03/2022 | TAPAN KUMAR MANDAL | 3.98 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its | SM/09639 | Retrofitting | Supply & delivery of portable multi parameter water quality testing device of the device of rural drinking water sources of 146 Nos. GP in Bankura District of west Bengal under PHE Dte |  |  | VCH/002839/2021-2022 | FHTC/9 | 09/03/2022 | 09/03/2022 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD | 13.33 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Mamra (16), Baradhara (17), Kukrakhondar (18), Gilirpahari (19), Tushkutari (20) & Hansapathar (21) mouzas by retrofitting of Water Supply Scheme for Parsola, Zone-A and its | SM/09639 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ with laying of HDPE pipeline in Parsola Mouza under Parsola, Zone-A by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000883/2023-2024 | 3011/BQA | 03/11/2023 | 18/12/2023 | BHATTACHARYYA CONSTRUCTION | 1.45 | 0 | 0 | 50
Total | [13 empty] | 254.17 | 0 | 0