## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura u | SM/09641 | Retrofitting | Work Order for Household survey in Barakhulia (188), Keotdhara (189), Balarampur (190), Siuli (191), Kuchakon (192), Bandiara (193), Arra (197), Kusbakra (198), Bhutsahar (199), Barisol (200), Srirampur (201), Beoncha (202), Parasol (203), Mandalgram (183), Patharkhamar (184), Shyampu (185), Pachaparar (186) & Bamunpathri (187) mouzas under Baricha, Zone-B to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 14) |  | Junior Engineer | ORD/000609/2021-2022 | 800/KSD | 14/12/2021 | 14/03/2022 | TAPAS DEY | 0.77 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura u | SM/09641 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in mouzas under Pathardoba, Zone-A & B and Baricha, Zone-B by retrofitting of Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 58 Nos. Total Household:- 7982 Nos. Name of Mouzas:- Under Pathardoba, Zone-A :- Parulia (91), Junkaria (92), Tentulia (93), Suknabad (94), Bhaduldoba (96), Memouli (97), Amakunda (98), Kaharan (99), Tarupur (100), Bansi (101), Ganrra (102), Sarasbakra (103), Sovarajpur (104), Sonakanda (105), Tapubaid (106), Jirabaid (107), Banskanali (108), Jharia (109), Ghoradhara (110), Machatora (111), Kamala (112), Sitarampur (113), Sushunia (114), Uparsol (115), Kansachora (116), Taldiha (117) Under Pathardoba, Zone-B:- Baniadoba (95), Shushunia (118), Karakanali (119), Jatiakanali (120), Koldoba (121), Pathardoba (122), Balarampur (123), Masatkhal (124), Rambani (125), Dudhia Doba (126), Namadudhiadoba (127), Badageria (128), Bagakhulia (138) & Kusumdunri (139) Under Baricha, Zone-B:- Barakhulia (188), Keotdhara (189), Balarampur (190), Siuli (191), Kuchakon (192), Bandiara (193), Arra (197), Kusbakra (198), Bhutsahar (199), Barisol (200), Srirampur (201), Beoncha (202), Parasol (203), Mandalgram (183), Patharkhamar (184), Shyampu (185), Pachaparar (186) & Bamunpathri (187) |  | Junior Engineer | ORD/000025/2022-2023 | 1085/BQA | 12/05/2022 | 11/07/2022 | GOPAL CHANDRA CHOWDHURY | 482.88 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura u | SM/09641 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000020/2022-2023 | 2036/BQA | 29/09/2022 | 29/09/2022 | Resource Division | 5.09 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas by retrofitting of Water Supply Scheme for Baricha, Zone-B and its adjoining Mouzas under Simlapal Water Supply Scheme (BRGF Ph-I) at Block- Simlapal, Dist.- Bankura u | SM/09641 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2022-2023 | 1836/BQA | 29/08/2022 | 29/08/2022 | Resource Division | 33.83 | 0 | 0 | 0
Total | [13 empty] | 522.56 | 0 | 0