## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | SM/09643 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Junbani (346), Rasunia (347), Jakpur (348), Nibra (353) & Indabinda (354) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 5 Nos. Total Household:- 362 Nos. |  | Junior Engineer | ORD/000387/2021-2022 | 441/BQA | 03/03/2022 | 02/04/2022 | UTTAM KUMAR SINHAMAHAPATRA | 14.48 | 3.42 | 23.59 | 0
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | SM/09643 | Retrofitting | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Junbani (346), Rasunia (347), Jakpur (348), Nibra (353) & Indabinda (354) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 5 Nos. Total Household:- 362 Nos. |  |  | VCH/000258/2022-2023 | FHTC/12 | 12/04/2022 |  | UTTAM KUMAR SINHAMAHAPATRA | 11.04 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | SM/09643 | Retrofitting | Work Order for Household survey in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas to provide ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 06) |  | Junior Engineer | ORD/000588/2021-2022 | 792/KSD | 14/12/2021 | 14/03/2022 | TAPAS DEY | 0.34 | 0.34 | 100 | 0
4 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | SM/09643 | Retrofitting | Work Order for Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Nibra (353) & Indabinda (354) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 22) |  | Junior Engineer | ORD/000206/2022-2023 | 1301/BQA | 15/06/2022 | 25/06/2022 | UTTAM KUMAR SINHAMAHAPATRA | 1.68 | 1.6 | 95.23 | 0
5 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | SM/09643 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Nibra (353) & Indabinda (354) mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 10) |  | Junior Engineer | ORD/000208/2022-2023 | 1289/BQA | 15/06/2022 | 25/06/2022 | UTTAM KUMAR SINHAMAHAPATRA | 4.83 | 4.46 | 92.3 | 0
6 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | SM/09643 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Gargarya (349) & Parulia (355) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-B) (Sl. No. 16) |  | Junior Engineer | ORD/000217/2022-2023 | 1295/BQA | 15/06/2022 | 25/06/2022 | TAPAN KUMAR MANDAL | 4.97 | 4.89 | 98.25 | 0
7 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | SM/09643 | Retrofitting | Work Order for Laying extra UPVC pipeline to cover Gargarya (349) & Parulia (355) mouzas for construction and commissioning of ?FHTC (Functional House Hold Tap Connection)? by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Part-A) (Sl. No. 14) |  | Junior Engineer | ORD/000216/2022-2023 | 1293/BQA | 15/06/2022 | 25/06/2022 | TAPAN KUMAR MANDAL | 4.91 | 4.85 | 98.73 | 0
8 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Junbani (346), Rasunia (347), Jakpur (348), Gargarya (349), Nibra (353), Indabinda (354) & Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A an | SM/09643 | Retrofitting | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in Gargarya (349) and Parulia (355) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) at Block- Sarenga, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Total Mouza:- 2 Nos. Total Household:- 653 Nos. |  | Junior Engineer | ORD/000203/2021-2022 | 3021/BQA | 29/11/2021 | 29/12/2021 | TAPAN KUMAR MANDAL | 28.09 | 28.04 | 99.81 | 0
Total | [13 empty] | 70.35 | 47.59 | 67.65