## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Dhengasole W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Bishnupur, Name of OHR - Dhengasole, No. of Mouza :- 05 nos. i.e. Dadasbari- 98, Jharia- 122, Bankati-123, Baraamlai-124 & Pedda-125, Total House Hold - 638 |  | Junior Engineer | ORD/000197/2021-2022 | 3027/BQA | 29/11/2021 | 29/12/2021 | BRINDABAN KONAR | 77.15 | 23.25 | 30.14 | 0
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Laying HDPE pipeline from Naba Chiyada village to Mukundapur Primary School and Dulalpur Primary School to increase pressure in Mukundapur (21) and Dulalpur (32) Mouzas for construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ by retrofitting Zone-I (Hatikheda) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/001237/2022-2023 | FHTC/23 | 23/09/2022 | 23/09/2022 | GON ASSOCIATES | 7.66 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Preparation of Detailed Project Report for Augmentation of Mukundapur Piped Water Supply Scheme, Block : Raipur, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) |  |  | VCH/001198/2022-2023 | FHTC/30 | 30/09/2022 | 30/09/2022 | SIRCON ENGINEERING SERVICES | 3.55 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Retrofitting works for creacion of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - III) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - III), No. of Mouza :- 01 no., (Kastora), Total House Hold- 55 nos. |  |  | VCH/000661/2022-2023 | FHTC/27 | 27/09/2022 | 27/09/2022 | S K FAZLUL ALAM | 4.81 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Construction & commissioning of Retrofitting works for creation of FHTC (Functional House Hold Tap Connection) in connection with JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos mousas (Bikpur, Kanki, Rajadal, Bangoan & Murgaboni) of piped water supply scheme for KANKI & its adjoining mouzas under Chhatna Block under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Chhatna, Name of OHR:- Kanki, No.of Mouza :- 05 (Rajadal Bongaon Bikpur, Murgaboni & Kanki). Total House Hold - 438 nos. |  |  | VCH/000884/2022-2023 | FHTC/23 | 23/09/2022 | 23/09/2022 | TAPAN KUMAR MANDAL | 7.26 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Extra HDPE pipe line to cover Amtha mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 04 |  |  | VCH/001241/2022-2023 | FHTC/28 | 28/09/2022 | 28/09/2022 | SIB SANKAR CHOWDHURY | 4.94 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Extra HDPE pipe line to cover Brindabonpur mouza of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. |  |  | VCH/001242/2022-2023 | FHTC/28 | 28/09/2022 | 28/09/2022 | SIB SANKAR CHOWDHURY | 4.98 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Water supply arrangement at different Anganwari Center laying pipe line & installation SSP under Lurka Zone -A |  |  | VCH/001243/2022-2023 | FHTC/23 | 23/09/2022 | 23/09/2022 | M/S ABU KADER KHAN | 3.14 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Laying extra HDPE Pipe Line from OHR zone - ll to Dehulka village to increase water pressure for 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Misson (JJM) and JAL SWAPNA of Salma (Zone - l) W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. , PHE Dte. |  |  | VCH/001199/2022-2023 | FHTC/30 | 30/09/2022 | 30/09/2022 | DAUD ALI KHAN | 4.92 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Extra HDPE pipe line to cover Harishpur & Mathur Beria mouzas of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of SAULIA (Zone - G) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. sl no - 09 |  |  | VCH/001236/2022-2023 | FHTC/28 | 28/09/2022 | 28/09/2022 | SIB SANKAR CHOWDHURY | 4.83 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Dhengasole (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 05 nos. mouzas (Dadasbari- 98, Jharia- 122, Bankati-123, Bara | SM/09644 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Salma (Zone - II) under Salma W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Name of OHR - Salma (Zone - II), No. of Mouza :- 01 no., Salma (Part), Habitation- Gobindpur, Total House Hold- 98 nos. |  |  | VCH/001228/2022-2023 | FHTC/27 | 27/09/2022 | 27/09/2022 | SAMIRUDDIN KHAN | 4.97 | 0 | 0 | 0
Total | [13 empty] | 128.22 | 23.25 | 18.14