## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Laying distribution system for Augmentation of Joypur ( JJM Revision ) Piped W/S. Scheme of Joypur Block under Bankura Division, PHE. Dte. ( PART-B) | Assistant Engineer | Junior Engineer | ORD/000041/2022-2023 | 1394/BQA | 27/06/2022 | 26/08/2022 | SIB SANKAR CHOWDHURY | 100.05 | 46.01 | 45.99 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYPUR W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Under JJM- 2020- 21 Fund. Block - Joypur, Name of OHR - Joypur, No. of Mouza :- 1 no. (Hirapur-44), Habitation's Name:- Kotalpara, Total House Hold - 30 |  | Junior Engineer | ORD/000505/2020-2021 | 214/VSD | 07/12/2020 | 28/12/2020 | NAYAN BARDHAN | 3.44 | 3.26 | 94.79 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYPUR W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Under JJM- 2020- 21 Fund. (Part-A) Block - Joypur, Name of OHR - Joypur, No. of Mouza :- 1 no. (Hirapur-44), Habitation's Name:- Dulepara & Telipara, Total House Hold -66. |  | Junior Engineer | ORD/000506/2020-2021 | 157/VSD | 18/09/2020 | 09/10/2020 | BIT ENTERPRISE | 4.71 | 4.29 | 90.89 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of JOYPUR W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Under JJM- 2020- 21 Fund. (Part-A) Block - Joypur, Name of OHR - Joypur, No. of Mouza :- 1 no. (Hirapur-44), Habitation's Name:- Napitpara, Total House Hold -65 |  | Junior Engineer | ORD/000507/2020-2021 | 158/VSD | 18/09/2020 | 09/10/2020 | SWAPAN KUMAR BIT | 4.62 | 4.06 | 87.92 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Construction of boundary wall approx 90 mtr long for Augmentation of Joypur water supply scheme (Head Work Site, New) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000379/2022-2023 | 54/BQA | 05/01/2023 | 19/02/2023 | BIJOY KOLEY | 5.28 | 4.78 | 90.49 | 50
6 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.40 m x 3.6 m) for Augmentation of Joypur Water Supply Scheme under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000382/2022-2023 | 55/BQA | 05/01/2023 | 05/04/2023 | SAYED PAHALOWAN | 6.54 | 6.3 | 96.27 | 65
7 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 2665/BQA | 22/09/2023 | 22/09/2023 | Resource Division | 42.53 | 0 | 0 | 0
8 | BANKURA |  | Bankura Mechanical | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Augmentation of Joypur Piped Water Supply Scheme. |  |  | BILL/00124/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Rising main with new D.I pipe under Joypur water supply scheme (Augmentation) under Joypur Block within Bishnupur Sub-Division under Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000385/2022-2023 | 56/BQA | 05/01/2023 | 19/02/2023 | RAFIKUL MONDAL | 23.74 | 13.8 | 58.12 | 20
10 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Supply of Various Type of Materials for construction and commissioning of RCC Over Head Reservoir of capacity 250 cum and staging height 20 mtr.with allied works for Augmentation of Joypur ( JJM Revision ) Piped W/S Scheme Joypur Block under Bishnupur Sub-Division of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000880/2023-2024 | 3008/BQA | 03/11/2023 | 18/12/2023 | SRIKANTA MONDAL | 5.95 | 5.95 | 100 | 90
11 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000152/2023-2024 | 111/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 20.82 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Restoration work of side shoulder due to damage caused for the laying of pipe line by PHE Department in the different stretches in Joypur baital road UNDER Bishnupur division PWDte. during the year 23-24 |  |  | BILL/02195/2023-2024 | FHTC/12 | 01/12/2023 | 01/12/2023 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 2.71 | 0 | 0 | 0
13 | BANKURA |  | Bankura Mechanical | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | New service connection at Katul of Joypur Piped Water Supply Scheme t/w-III ,Katul of joypur block under BMD PHE Dte. |  |  | BILL/00381/2024-2025 | BP-2024-25-89 | 11/06/2024 | 11/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.27 | 0 | 0 | 0
14 | BANKURA |  | Bankura Mechanical | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Joypur Pump house-II |  |  | BILL/01508/2023-2024 | BP-2023-24-108 | 15/02/2024 | 15/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.59 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Retrofitting works for creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Joypur W/S Scheme under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Joypur, Name of OHR - Joypur, No. of Mouza :- 7 nos. i.e.Kalabani-12,Padumpur-14,Rajsol-15,Salda-35,Joypur-36,Bamangram-40,Gokulnagar-43, Total House Hold - 3380 | Assistant Engineer | Junior Engineer | ORD/000389/2021-2022 | 200/BQA | 01/02/2022 | 08/05/2024 | M/S CARE | 179.91 | 63.17 | 35.11 | 5
16 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Laying distribution system for Augmentation of Joypur ( JJM Revision ) Piped W/S. Scheme of Joypur Block under Bankura Division, PHE. Dte. ( PART-A) | Assistant Engineer | Junior Engineer | ORD/000040/2022-2023 | 1381/BQA | 27/06/2022 | 01/11/2025 | DEBAKI RANJAN SARKAR | 100 | 43.65 | 43.65 | 80
17 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Construction of Office cum Godown with sanitary and water supply arrangement at Head Work Site (New) of 60 sqmtr. (approx) area at water supply scheme for surface water based for Augmentation of Joypur water supply scheme under Bishnupur Sub-Division, Bankura Division PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000377/2022-2023 | 53BQA | 05/01/2023 | 01/07/2025 | UTTAM KUMAR SINHAMAHAPATRA | 12.53 | 7.78 | 62.1 | 35
18 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Sinking of 1 no 300mm X 200mm X 250m deep Tubewell by Rig boring system method including interconnection with 100 mm dia. G.I. Pipe at New Head Work Site for Augmetation of Joypur( JJM Revision ) Piped water supply scheme under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000086/2023-2024 | 1067/BQA | 04/05/2023 | 01/04/2025 | I.R.CONSTRUCTION | 19.03 | 0 | 0 | 85
19 | BANKURA |  | Bankura Mechanical | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmantation of Joypur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Joypur Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000425/2023-2024 | 1686/BMD | 27/07/2023 | 02/12/2025 | PRADIP KUMAR DHABAL | 39.53 | 30.88 | 78.13 | 30
20 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Additional work of Road Crossing for Jack Pussing of Augumentation of Joypur Water Supply Scheme under Joypur Block under Bishnupur Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000871/2023-2024 | 3003/BQA | 06/11/2023 | 03/11/2024 | SIBSANKAR CHOWDHURY | 34.14 | 0 | 0 | 85
21 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Renovation of RCC Elevated Over Head Reservoir of 273 cum capacity with staging height 20 m and other allied works Augmentation of Joypur water supply scheme within Bishnupur Sub-Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000344/2025-2026 | 1805/BQA | 19/08/2025 | 17/11/2025 | SWAPAN KUMAR BIT | 11.69 | 0 | 0 | 90
22 | BANKURA |  | Bankura Division | Augmentation of Joypur Piped Water Supply Scheme. | SM/09878 | Augmentation | Construction and commissioning of RCC Over Head Reservoir of capacity 250 cum and staging height 20 mtr.with allied works for Augmentation of Joypur ( JJM Revision ) Piped W/S under Joypur Block of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000423/2022-2023 | 181/BQA | 30/01/2023 | 27/10/2023 | SRIKANTA MONDAL | 70.43 | 70.34 | 99.88 | 60
Total | [13 empty] | 695.51 | 304.27 | 43.75