## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas | SM/09879 | Augmentation | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 300 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Bikna and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer |  | ORD/001070/2022-2023 | 359/BSD | 13/04/2022 | 28/04/2022 | ASIS ENTERPRISE | 1.85 | 0 | 0 | 100
2 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas | SM/09879 | Augmentation | Payment to Rail |  |  | BILL/00020/2023-2024 | FHTC/17 | 17/04/2023 | 17/04/2023 | SOUTH EASTERN RAILWAY | 5.87 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas | SM/09879 | Augmentation | Survey work for Augmentation for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) for 03 nos. Mouzas of proposed Augmentation of piped water supply scheme for Bikna and its adjoining mouzas under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block-Bankura -II , District -Bankura. Block - Bankura- II, Name of OHR - Bikna Water Supply Scheme, No. of Mouza :- 03 nos, Bikna (235), Kuraria (254), Katnar (255). | Assistant Engineer | Junior Engineer | ORD/000272/2023-2024 | 519/BSD | 12/06/2023 | 11/08/2023 | TAPAS DEY | 0.45 | 0 | 0 | 100
4 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas | SM/09879 | Augmentation | Road Crossing work by verious dia MS carrier pipe by Jack pushing method, inetrconnection of MS carrier pipe with UPVC pipeline including fabrication of MS pipe & allied works for Augmentation of Bikna Piped Water Supply Scheme (JJM Revision) under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001266/2023-2024 | 693/BQA | 28/02/2024 | 13/04/2024 | PARAMESWAR CHOWDHURY | 34.8 | 0 | 0 | 85
5 | BANKURA |  | Bankura Mechanical | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas | SM/09879 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of gaseous chlorination system and other electromechanical acessories at OHR site of Augmentation works for Bikna and its adjoining mouzas Water Supply Scheme (Phase- I). under Bankura Mechanical Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000319/2024-2025 | 860/BMD | 29/08/2024 | 27/12/2024 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 41.19 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas | SM/09879 | Augmentation | Laying Rising Main DI (K9) pipe & construction of CWR (50 CUM CAPACITY) with plinth protection for the proposed Augmentation of piped water supply scheme for Bikna and its adjoining mouzas under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block-Bankura -II , District -Bankura ( Single compartment , Size of Compartment -Length 5mtr , Width-5mtr , Depth -2.5 mtr ) ( Sl.No-04) | Assistant Engineer | Junior Engineer | ORD/000445/2021-2022 | 525/BQA | 10/03/2022 | 19/01/2023 | SAIKAT CHOWDHURY | 13.71 | 0 | 0 | 51
7 | BANKURA |  | Bankura Division | Augmentation of piped water supply schemes for Bikna and its adjoining mouzas | SM/09879 | Augmentation | Laying DI (K7) & UPVC pipe line for distribution system & Construction and commissioning of 300 m³ capacity R.C.C OHR (based on Departmental Design Ref. Drawing No. PC- 1/OHR/7/2012 (Sheet 1 &2)with 20 mtr staging height including foundation, pipeline connection and cost of pipes , specials etc.and allied works for the proposed Augmentation of piped water supply scheme for Bikna and its adjoining mouzas under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block-Bankura -II , District -Bankura PART -A and Construction and commissioning of 300 m³ capacity R.C.C OHR (based on Departmental Design Ref. Drawing No. PC- 1/OHR/7/2012 (Sheet 1 &2)with 20 mtr staging height including foundation, pipeline connection and cost of pipes , specials etc.and allied works for the proposed Augmentation of piped water supply scheme for Bikna and its adjoining mouzas under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. Block-Bankura -II , District -Bankura PART - B | Assistant Engineer | Junior Engineer | ORD/000077/2022-2023 | 1989/BQA | 27/09/2022 | 01/04/2025 | PARAMESWAR CHOWDHURY | 193.56 | 0 | 0 | 60
Total | [13 empty] | 291.43 | 0 | 0