## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Construction of boundary wall approx 30 mtr long for Augmentation of Joyrambati water supply scheme (2nd T/W Site) under Bishnupur Sub Division of Bankura Division, PHE Dte. (2nd Call) TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 | Assistant Engineer | Junior Engineer | ORD/000015/2023-2024 | 764/BQA | 04/04/2023 | 04/05/2023 | MRITYUNJOY HAZRA | 1.66 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Construction of Ground Level Reservoir (capacity 50 m3) for Matri Mandir, Joyrambati, Bankura under Joyrambati water supply scheme within Bishnupur Sub-Division of Bankura Division PHE. Dte. |  | Junior Engineer | ORD/000453/2021-2022 | 661/BQA | 23/03/2022 | 21/06/2022 | MOHAN KUMAR ROY | 16.99 | 14.38 | 84.62 | 20
3 | BANKURA |  | Bankura Mechanical | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Augmentation of Jayrambati Piped Water Supply Scheme. |  |  | BILL/00133/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.6 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Augmentation of Jayrambati Piped Water Supply Scheme. |  |  | BILL/00123/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM Revision) for Augmentation of Joyrambati W/S Scheme Block- Kotulpur under Bishnupur Sub - Division of Bankura Division, PHE Dte. TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 Block -Kotulpur, Name of OHR -Joyrambati, No. of Mouza :- 4 nos. i.e. (i) Joyrambati - J.L No-164 , (ii) Haldi J.L. No-165, (iii) Malpur J.L No-166 & (iv) Masinapur J.L No-167 . Total House Hold - 1287 | Assistant Engineer | Junior Engineer | ORD/000422/2022-2023 | 179/BQA | 30/01/2023 | 24/05/2024 | DIPAYAN DEY | 66.36 | 27.14 | 40.9 | 35
6 | BANKURA |  | Bankura Mechanical | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Acceptance cum Formal work order for the work of Name of Work:Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Joyrambati piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000175/2023-2024 | 935/BMD | 12/05/2023 | 08/11/2023 | KASHINATH DEY | 29.69 | 22.96 | 77.33 | 77
7 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Laying distribution system including allied works of Augmentation of Joyrambati Piped W/S. Scheme (JJM Revesion ) at Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000051/2023-2024 | 901/BQA | 20/04/2023 | 21/01/2024 | BISWARUP BOSE | 110.15 | 109.8 | 99.68 | 45
8 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Emergent repairing for laying of pipe line by the PHE department at Joyrambati-Kamarpukur road at Malpur Prathamik Vidyalaya under Bishnupur Division PWD in the District of Bankura during the year 2023-2024 |  |  | BILL/02189/2023-2024 | FHTC/12 | 01/12/2023 | 01/12/2023 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 0.96 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Restoration work of side shoulder due to damage caused for the laying of pipeline by PHE department in the different stretches in joyrambati - kamarpukur road under Bishnupur division P.W.Dte. in the district of Bankura . |  |  | BILL/02424/2023-2024 | FHTC/02 | 02/02/2024 | 02/02/2024 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 43.62 | 0 | 0 | 0
Total | [13 empty] | 271.05 | 174.28 | 64.3