## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Construction of boundary wall approx 30 mtr long for Augmentation of Joyrambati water supply scheme (2nd T/W Site) under Bishnupur Sub Division of Bankura Division, PHE Dte. (2nd Call) TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 | Assistant Engineer | Junior Engineer | ORD/000015/2023-2024 | 764/BQA | 04/04/2023 | 04/05/2023 | MRITYUNJOY HAZRA | 1.66 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Construction of Ground Level Reservoir (capacity 50 m3) for Matri Mandir, Joyrambati, Bankura under Joyrambati water supply scheme within Bishnupur Sub-Division of Bankura Division PHE. Dte. |  | Junior Engineer | ORD/000453/2021-2022 | 661/BQA | 23/03/2022 | 21/06/2022 | MOHAN KUMAR ROY | 16.99 | 14.38 | 84.62 | 20
3 | BANKURA |  | Bankura Mechanical | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Augmentation of Jayrambati Piped Water Supply Scheme. |  |  | BILL/00133/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.6 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Augmentation of Jayrambati Piped Water Supply Scheme. |  |  | BILL/00123/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM Revision) for Augmentation of Joyrambati W/S Scheme Block- Kotulpur under Bishnupur Sub - Division of Bankura Division, PHE Dte. TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 Block -Kotulpur, Name of OHR -Joyrambati, No. of Mouza :- 4 nos. i.e. (i) Joyrambati - J.L No-164 , (ii) Haldi J.L. No-165, (iii) Malpur J.L No-166 & (iv) Masinapur J.L No-167 . Total House Hold - 1287 | Assistant Engineer | Junior Engineer | ORD/000422/2022-2023 | 179/BQA | 30/01/2023 | 24/05/2024 | DIPAYAN DEY | 66.36 | 27.14 | 40.9 | 35
6 | BANKURA |  | Bankura Mechanical | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Acceptance cum Formal work order for the work of Name of Work:Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Joyrambati piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Kotulpur Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000175/2023-2024 | 935/BMD | 12/05/2023 | 08/11/2023 | KASHINATH DEY | 29.69 | 22.96 | 77.33 | 77
7 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Laying distribution system including allied works of Augmentation of Joyrambati Piped W/S. Scheme (JJM Revesion ) at Kotulpur Block under Bishnupur Sub-Division of Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000051/2023-2024 | 901/BQA | 20/04/2023 | 21/01/2024 | BISWARUP BOSE | 110.15 | 109.8 | 99.68 | 45
8 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Emergent repairing for laying of pipe line by the PHE department at Joyrambati-Kamarpukur road at Malpur Prathamik Vidyalaya under Bishnupur Division PWD in the District of Bankura during the year 2023-2024 |  |  | BILL/02189/2023-2024 | FHTC/12 | 01/12/2023 | 01/12/2023 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 0.96 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Restoration work of side shoulder due to damage caused for the laying of pipeline by PHE department in the different stretches in joyrambati - kamarpukur road under Bishnupur division P.W.Dte. in the district of Bankura . |  |  | BILL/02424/2023-2024 | FHTC/02 | 02/02/2024 | 02/02/2024 | EXECUTIVE ENGINEER , BISHNUPUR DIVISION P.W.DTE. | 43.62 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation of Jayrambati Piped Water Supply Scheme. | SM/09880 | Augmentation | Construction of Office cum Godown with sanitary and water supply arrangement at Head Work Site of 60 sqmtr. (approx) area at water supply scheme for surface water based for Augmentation of Joyrambati water supply scheme under Bishnupur Sub-Division, Bankura Division PHE Dte. (2nd Call) TSM No.-TSM/005083 , AAFS Project Id :- PH212246197M000 | Assistant Engineer | Junior Engineer | ORD/000014/2023-2024 | 763/BQA | 04/04/2023 | 01/04/2025 | M/S T.P. HAZRA & SONS | 12.53 | 6.85 | 54.66 | 20
Total | [13 empty] | 283.58 | 181.13 | 63.87