## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | Work order for Preparation of D.P.R.(consultancy work) in connection with the augmentation of ground water based piped water supply scheme for Patrasayer to accommodate FHTC under Jal Sapno Mission under Patrasayer Block in Bankura District under Bankura Division, PHE Dte. (Sl. No. 2) [Estimated Cost Rs. Quotated Rate] |  | Junior Engineer | ORD/000652/2021-2022 | 424/B/VSD | 23/09/2021 | 03/10/2021 | SIRCON ENGINEERING SERVICES | 2.59 | 2.59 | 100 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | Repairing of one no. pump house for augmentation of Patrasayer water supply scheme under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000388/2022-2023 | 69/BQA | 05/01/2023 | 19/02/2023 | MOHAN KUMAR ROY | 2.07 | 1.3 | 62.96 | 95
3 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | "Construction of boundary wall approx 126 mtr long for augmentation of Patrasayer water supply scheme (pump house no 2) under Bishnupur Sub Division of Bankura Division, PHE Dte. (TSM/008991) (SM/09926) (AAFS- PH212246951M000)" | Assistant Engineer | Junior Engineer | ORD/000560/2022-2023 | 523/BQA | 14/03/2023 | 13/04/2023 | MUNMUN UPADHYAY | 7.24 | 7.23 | 99.89 | 89
4 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Patrasayer W/S Scheme under Bishnupur Sub-Division, P.H.E. Dte. of Bankura Division P.H.E. Dte. (2nd Call) (Sl. No. 01) OHR Capacity- 400 m3 |  | Junior Engineer | ORD/000652/2022-2023 | 144//VSD | 18/05/2022 | 02/06/2022 | G.MITRA AND ASSOCIATES | 1.4 | 1.4 | 100 | 0
5 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000147/2023-2024 | 3345/BQA | 06/12/2023 | 06/12/2023 | Resource Division | 38.12 | 0 | 0 | 0
6 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. |  |  | BILL/00126/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.5 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.50 m x 4.5 m) for augmentation of Patrasayer Water Supply Scheme under Bishnupur Sub Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000386/2022-2023 | 68/BQA | 05/01/2023 | 28/06/2024 | BIDHAN BANERJEE | 6.54 | 4.73 | 72.29 | 85
8 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | SOIL INVESTIGATION FOR 19 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN PATRASAYER BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer |  | ORD/000415/2022-2023 | 353/BQA | 21/02/2023 | 23/03/2023 | GLORY ENGINEERS SYNDICATE | 15.38 | 15.38 | 100 | 70
9 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | Patrasayer Market Road from 0.00 kmp to 2.50 kmp. restoration work of both side of road due to laying of pipeline by Bankura Division. PHE Dte. Ref: EE/Bankura Highway Division P.W(Roads) Dte. Office Memo No- 1330 Dated 07.1 1.2023. |  |  | BILL/00945/2024-2025 | BP-316/2024-25 | 25/09/2024 | 25/09/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 43.98 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | Bishbupur Patrasayer market road from 22.00 kmp 28.00 kmp restoration work of both side of road due to laying of pipeline by Bankura Division PHE Dte. under Bankura Highway Division in the district of Bankura |  |  | BILL/02260/2023-2024 | FHTC/12 | 13/12/2023 | 13/12/2023 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 18.25 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | Construction & Commissioning of 400 m3 capacity 20 Mtr. staging height RCC Over Head Reservoir (Ref. of Drg.no.-PC-I/OHR/11/2012(Rev-01){Sheet-1/2 &2/2} of SE,PC-I,PHE Dte.) staging height 20 mtr. with Laying Distribution System as per LDS drawing, including FHTC works for Augmentation of Patrasayer piped water supply scheme at Patrasayer Block of Bishnupur Sub - Division under Bankura Division, PHE. Dte. | Assistant Engineer | Junior Engineer | ORD/000050/2023-2024 | 899/BQA | 20/04/2023 | 01/11/2025 | DEBAKI RANJAN SARKAR | 345 | 291.77 | 84.57 | 96
12 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | Construction of boundary wall approx 203 mtr long for augmentation of Patrasayer water supply scheme (pump house no 1) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000391/2022-2023 | 70/BQA | 05/01/2023 | 18/02/2025 | MOHAN KUMAR ROY | 14.28 | 5.6 | 39.23 | 100
13 | BANKURA |  | Bankura Mechanical | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR PATRASAYER TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER PATESAYER BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09926 | Augmentation | Acceptance cum Formal work order for the work of installation of Pumping machineries with other electro-mechanical accessories for ground base piped water supply scheme for Patrasayar to commanded FSTC under Jal Swapna mission under Patarasyar Block in Bankura District under Bankura Mechanical Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000191/2023-2024 | 1014/BMD | 22/05/2023 | 06/05/2026 | INDRAJIT MITRA | 19.94 | 10.79 | 54.11 | 54
Total | [13 empty] | 516.3 | 340.81 | 66.01