## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | Augmentation | Retrofitting works for various Anganwari Center's & School under Moynapur W/S Scheme Bishnupur Sub - Division of Bankura Division, PHE Dte. |  | Junior Engineer | ORD/000072/2022-2023 | 136/VSD | 12/05/2022 | 27/05/2022 | SWAPAN KUMAR DE | 0.49 | 0.49 | 100 | 0
2 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | Augmentation | Work order for Preparation of D.P.R.(consultancy work) in connection with the augmentation of ground water based piped water supply scheme for Moynapur to accommodate FHTC under Jal Sapno Mission under Jaypur Block in Bankura District under Bankura Division, PHE Dte. (Sl. No. 1) [Estimated Cost Rs. Quotated Rate] |  | Junior Engineer | ORD/000651/2021-2022 | 424/A/VSD | 23/09/2021 | 03/10/2021 | SIRCON ENGINEERING SERVICES | 2.51 | 2.51 | 100 | 0
3 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | Augmentation | Laying distribution system Augmentation of Moynapur Piped W/S. Scheme (JJM Revesion ) at Moynapur, Joypur Block under Bankura Division, PHE. Dte. |  | Junior Engineer | ORD/000297/2022-2023 | 06/BQA | 03/01/2023 | 03/04/2023 | S B ASSOCIATES | 80.46 | 71.03 | 88.28 | 0
4 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | Augmentation | Construction of boundary wall approx 90 mtr long for Augmentation of Moynapur water supply scheme (2nd T/W Site) under Bishnupur Sub Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000384/2022-2023 | 67/BQA | 05/01/2023 | 04/02/2023 | GOURANGA NANDI | 5.28 | 5.14 | 97.38 | 0
5 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | Augmentation | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Belitore W/S Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. Block - Barjora, G.P -Chandar, Name of Village- Kadakuli Roy Para, Chandar Rail line para, school , health center, Total House Hold -52. |  | Junior Engineer | ORD/000471/2020-2021 | 10/BSD | 06/01/2021 | 27/01/2021 | SANJOY MONDAL | 4.8 | 4.79 | 99.78 | 0
6 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | Augmentation | Creation of 'FHTC (Funtional House Hold Tap Connection)' in connection with Jal Jeevan Mission (JJM Revision) for augmentation of Moynapur W/S Scheme Block- Joypur under Bishnupur Sub - Division of Bankura Division, PHE Dte. TSM No.-TSM/008990 , AAFS Project Id :- PH212246951M000 Block -Joypur, Name of OHR -Moynapur, No. of Mouza :- 1 nos. i.e. Moynapur-J.L No-120. Total House Hold - 1224 | Assistant Engineer | Junior Engineer | ORD/000419/2022-2023 | 180/BQA | 30/01/2023 | 31/03/2023 | TAPAN KUMAR MANDAL | 51.02 | 51.01 | 100 | 100
7 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | Augmentation | Soil Investigation work for the proposed construction of RCC Over Head Reservoir under Moynapur W/S Scheme under Bishnupur Sub-Division, P.H.E. Dte. of Bankura Division P.H.E. Dte. (2nd Call) (Sl. No. 02) OHR Capacity- 300 m3 |  | Junior Engineer | ORD/000654/2022-2023 | 145//VSD | 18/05/2022 | 02/06/2022 | AGAC | 1.4 | 1.4 | 100 | 0
8 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | Augmentation | Providing FHTC, Sinking of 1 no Tubewell and Construction of Pump House for Augmentation of Moynapur Water Supply Scheme. | Assistant Engineer | Junior Engineer | ORD/001364/2024-2025 | 3126/BQA | 19/12/2024 | 19/03/2025 | SANJOY PATRA | 48.63 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | Augmentation | Supply of Various Type Materials for Construction of 300 m3 capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for MOYNAPUR mouzas under MOYNAPUR W/S. scheme, at JOYPUR Block, Within BISHNUPUR Sub-Division,under BANKURA Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001149/2023-2024 | 354/BQA | 06/02/2024 | 07/03/2024 | SANJOY PATRA | 6.02 | 5.99 | 99.52 | 75
10 | BANKURA |  | Bankura Division | AUGMENTATION OF GROUND WATER BASE PIPE WATER SUPPLY SCHEME FOR MOYNAPUR TO ACCOMMODATE FHTC UNDER JALSAPNO MISSION UNDER JAYPUR BLOCK IN BANKURA DISTRICT UNDER BANKURA DIVISION P.H.E.DTE. | SM/09927 | Augmentation | Construction of 300 m3 capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for MOYNAPUR mouzas under MOYNAPUR W/S. scheme, at JOYPUR Block, Within BISHNUPUR Sub-Division,under BANKURA Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000267/2022-2023 | 2322/BQA | 08/12/2022 | 22/12/2025 | SANJOY PATRA | 82.13 | 78.3 | 95.33 | 95
Total | [13 empty] | 282.74 | 220.66 | 78.04