## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Somsar (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos Mouza Bhagabatipur - 01, Palashdanga - 03, Kumna - 04 of | SM/10041 | Retrofitting | "Creation of 'FHTC (Funtional House Hold Tap Connection)' of left out Mouza, in connection with Jal Jeevan Mission of Somsar W/S Scheme (BRGF Ph-I) Block- Indas under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block -Bishnupur, Name of OHR -Dhengasole, No. of Mouza :- 3 nos. i.e. (i) Bhagabatipur J.L No-01, (ii) Palashdanga J.L No-03, (iii) Kumna JL No-04. Total House Hold - 518 SM/10041 " | Assistant Engineer | Junior Engineer | ORD/000156/2023-2024 | 1354/BQA | 02/06/2023 | 01/08/2023 | S B ASSOCIATES | 71.74 | 71.72 | 99.97 | 91
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Somsar (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos Mouza Bhagabatipur - 01, Palashdanga - 03, Kumna - 04 of | SM/10041 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Somsar W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Naldanga No. of Mouza :- 01 no. mouzas (i.e. Palashdanga 03) , Total House Hold - 75 | Assistant Engineer | Junior Engineer | ORD/001111/2022-2023 | 137A/VSD | 12/05/2022 | 02/06/2022 | SANU KARMAKAR | 4.81 | 4.48 | 93.16 | 85
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Somsar (BRGF Ph - I project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 03 nos Mouza Bhagabatipur - 01, Palashdanga - 03, Kumna - 04 of | SM/10041 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of Somsar W/S Scheme (BRGF ph - I project) under Bishnupur Sub - Division of Bankura Division, PHE Dte. Block - Indas, Name of OHR - Naldanga No. of Mouza :- 01 no. mouzas (i.e. Palashdanga 03) , Total House Hold - 70 | Assistant Engineer | Junior Engineer | ORD/001110/2022-2023 | 137/VSD | 12/05/2022 | 02/06/2022 | AJIT KUMAR DUTTA | 4.54 | 4.48 | 98.59 | 85
Total | [13 empty] | 81.09 | 80.67 | 99.49