## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Construction of Pump House (Switch Room cum Chlorine Room) with Sanitary & Water Supply arrangement (size 5.50 m x 4.5 m) for augmentation of Nabakishore Water Supply Scheme under Bishnupur Sub Division of Bankura Division P.H.E. Dte. (TSM/008518) (SM/10290) (AAFS- PH212245028S000) | Assistant Engineer | Junior Engineer | ORD/000380/2022-2023 | 65/BQA | 05/01/2023 | 05/04/2023 | SANU KARMAKAR | 6.51 | 0 | 0 | 86
2 | BANKURA |  | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Repairing of one no pump house for augmentation of Nabakishore water supply scheme under Bishnupur Sub Division of Bankura Division, PHE Dte. (TSM/008518) (SM/10290) (AAFS- PH212245028S000) | Assistant Engineer | Junior Engineer | ORD/000559/2022-2023 | 522/BQA | 14/03/2023 | 28/04/2023 | MOHAN KUMAR ROY | 2.01 | 0 | 0 | 85
3 | BANKURA |  | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 3345/BQA | 06/12/2023 | 06/12/2023 | Resource Division | 50.07 | 0 | 0 | 0
4 | BANKURA |  | Bankura Mechanical | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) |  |  | BILL/00121/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.4 | 0 | 0 | 0
5 | BANKURA |  | Bankura Mechanical | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Acceptance cum Formal work order for the work of Name of Work:Providing, installation of Pumping machineries with other electro-mechanical accessories for Augmantation of Nabakishore Ground Base piped water supply scheme under JJM program under Bankura Mechanical Division, PHE Dte Block : Patrasayar, Dist: Bankura | Assistant Engineer | Junior Engineer | ORD/000174/2023-2024 | 934/BMD | 12/05/2023 | 08/11/2023 | M/S NABIN GOPAL SENGUPTA | 56.49 | 0 | 0 | 76
6 | BANKURA |  | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Construction of boundary wall approx 132 mtr long for augmentation of Nabakishore water supply scheme (pump house no 1) under Bishnupur Sub Division of Bankura Division, PHE Dte. (TSM/008518) (SM/10290) (AAFS- PH212245028S000) | Assistant Engineer | Junior Engineer | ORD/000378/2022-2023 | 64/BQA | 05/01/2023 | 04/02/2023 | GANGADHAR MONDAL | 9.38 | 0 | 0 | 10
7 | BANKURA |  | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Construction of boundary wall approx 60 mtr long at 3rd TW site of Augmentation of Nabakishore water supply scheme within Patrasayer Block under Bishnupur Sub-Division of Bankura Division P.H.E Dte. | Assistant Engineer | Junior Engineer | ORD/000195/2024-2025 | 1868/BQA | 12/07/2024 | 11/08/2024 | M/S ABU KADER KHAN | 3.84 | 0 | 0 | 90
8 | BANKURA |  | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000153/2023-2024 | 111/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 28.91 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Patrasayer market road from 0.00 kmp 02.50 kmp restoration work of both side of road due to laying of pipeline by Bankura Division PHE Dte. under Bankura Highway Division in the district of Bankura, (1) Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) |  |  | BILL/02261/2023-2024 | FHTC/12 | 13/12/2023 | 13/12/2023 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 46.31 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Construction & Commissioning of 700 m3 capacity 20 Mtr. staging height RCC Over Head Reservoir (Ref. of Drg.no.-PC-I/OHR/6/2012(Rev-01){Sheet-1/2 &2/2} of SE,PC-I,PHE Dte.) staging height 20 mtr. with Laying Distribution System as per LDS drawing, including FHTC works for Augmentation of Nabakishore Piped Water Supply Scheme under Patrasayer Block of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000444/2023-2024 | 2277/BQA | 01/08/2023 | 30/10/2025 | SATYANARAYAN ENGINEERS' CO-OP.SOCIETY LTD | 623.97 | 0 | 0 | 89
11 | BANKURA |  | Bankura Division | Augmentation of Nabakishore Ground water based piped water supply scheme (JJM REVISION) | SM/10290 | Augmentation | Sinking of 2 Nos. Tubewell (Rotary Method) with construction of 2 Nos. Pump House & Boundary Wall and Laying of Distribution System under Augmentation of Nabakishore Water Supply Scheme under Jal Jeevan Mission (JJM) within Patrasayer Block under Bishnupur Sub-division of Bankura Division, P.H.E. Dte. (SM/10290) | Assistant Engineer | Junior Engineer | ORD/000103/2025-2026 | 1232/BQA | 02/06/2025 | 16/02/2026 | M/S S. CHOUDHURY | 158.01 | 0 | 0 | 40
Total | [13 empty] | 986.91 | 0 | 0