## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Sinking of 07 no. 200 mm dia. X 6.0 Mtr. depth Horizontal River Bed Tube Well & Supplying Laying 100 mm dia G.I connecting Main including supply and Erecting of 40 mm dia G I Pipe for Guard pilling from River bed T/W to Manifold for Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000466/2021-2022 | 784/BQA | 31/03/2022 | 30/04/2022 | GOPAL CHANDRA CHOWDHURY | 57.75 | 52.65 | 91.16 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Laying HDPE Pipe Line from Bamuntore pump house to Narayanpur more to Iswada village for water supply arrangement at Narayanpur & Iswada village under augamentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000276/2022-2023 | 08/BQA | 03/01/2023 | 17/02/2023 | RAHUL CHATERJEE | 8.95 | 8.88 | 99.24 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Construction of CWR (250 CUM CAPACITY) with plinth protection and other allied works for Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. (For Zone -I) | Assistant Engineer | Junior Engineer | ORD/000068/2022-2023 | 1696/BQA | 28/07/2022 | 26/09/2022 | SAIKAT CHOWDHURY | 50.47 | 39.45 | 78.16 | 90
4 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | laying extra HDPE Pipe Line to Cover Narayanpur mouza under augamentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000374/2022-2023 | 51/BQA | 05/01/2023 | 19/02/2023 | SWAPAN KUMAR CHANDRA | 3.59 | 3.59 | 99.85 | 100
5 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Laying extra HDPE Pipe Line to cover Iswada mouza under augamentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000375/2022-2023 | 52/BQA | 05/01/2023 | 19/02/2023 | S K FAZLUL ALAM | 4.88 | 4.88 | 100 | 80
6 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2022-2023 | 1953/BQA | 19/09/2022 | 19/09/2022 | Resource Division | 39.9 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000047/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 232.29 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | 01 (One) no. Diesel / LPG / CNG driven Luxury Taxi / Bolero / Scorpio / Innova on hire basis for inspection of JJM works across Bankura district of Deputy Superintending Engineer, PIU, WBDWSIP, PHE Dte. For the period from 01/10/2023 to 31/03/2024 (183 Days). | Assistant Engineer | Junior Engineer | ORD/000719/2023-2024 | 1016/BSD | 29/09/2023 | 30/03/2024 | TARUN KUMAR BHATTACHARYYA | 0.87 | 2.2 | 253.66 | 100
9 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from 10/08/2023 to 09/02/2024 (184 Days). | Assistant Engineer | Junior Engineer | ORD/000621/2023-2024 | 807/BSD | 10/08/2023 | 10/02/2024 | GOUTAM GHOSH | 0.87 | 2.42 | 276.92 | 0
10 | BANKURA |  | Bankura Mechanical | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Formal work order for the work of Providing and installation of High Lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation of subsurface water based water supply scheme Saltora for providing FHTC in Saltora Block under Bankura Mechanical Division PHE Dte, Block: Saltora Dist : Bankura. | Assistant Engineer | Junior Engineer 1 | ORD/000614/2023-2024 | 2070/BMD | 12/09/2023 | 10/03/2024 | DAS ENTERPRISE | 303.87 | 222.57 | 73.24 | 40
11 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Continuation for Supply of 01 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for official use of the Assistant Engineer, Bankura Head Quarter under Bankura Division P.H.E. Dte. for the period from 01/12/2022 to 30/11/2023 (One Year) | Assistant Engineer |  | ORD/001176/2022-2023 | 10\BQA(H.Q.) | 28/11/2022 | 28/11/2023 | MITALI CHHATAIT PARAMANIK | 1.73 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Continuation for engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from 01/05/2024 to 31/05/2024 (31 Days). | Assistant Engineer | Junior Engineer | ORD/000111/2024-2025 | 533/BSD | 30/04/2024 | 31/05/2024 | GOUTAM GHOSH | 0.15 | 0.39 | 264.5 | 0
13 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Continuation for Supply of 01 (One) No. Diesel/ LPG/ CNG driven Luxury Taxi / Bolero/ Scorpio on hire basis for official use of the Assistant Engineer, Bankura Head Quarter under Bankura Division P.H.E. Dte. for the period from 01/12/2023 to 30/11/2024 (One Year) |  | Junior Engineer | ORD/001627/2023-2024 | 55\BQA(H.Q.) | 29/11/2023 | 29/11/2024 | MITALI CHHATAIT PARAMANIK | 1.74 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Continuation for engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from 10/02/2024 to 31/03/2024 (51 Days). | Assistant Engineer | Junior Engineer | ORD/001451/2023-2024 | 249/BSD | 09/02/2024 | 31/03/2024 | GOUTAM GHOSH | 0.24 | 0.64 | 263.5 | 0
15 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Continuation for engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from 01/04/2024 to 30/04/2024 (30 Days). | Assistant Engineer | Junior Engineer | ORD/001562/2023-2024 | 473/BSD | 28/03/2024 | 27/04/2024 | GOUTAM GHOSH | 0.14 | 0.37 | 256.88 | 0
16 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Continuation for engagement of 01 (One) no. additional vehicle on hire basis for official use for the office of the Assistant Engineer, Bankura Sadar Sub- Division, P.H.E. Dte. For the period from 01/06/2024 to 30/06/2024 (30 Days). | Assistant Engineer | Junior Engineer | ORD/001334/2024-2025 | 607/BSD | 28/05/2024 | 27/06/2024 | GOUTAM GHOSH | 0.14 | 0.39 | 276.38 | 0
17 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Supply of fitting including carriage and delivary at site for Augmentation of sub surface water based water supply scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division,P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001439/2023-2024 | 692/BQA | 27/02/2024 | 28/03/2024 | APEX ENTERPRISE | 30.63 | 30.63 | 100 | 20
18 | BANKURA |  | Bankura Mechanical | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Upward revision of contract Demand from 120KVA to 155 KVA at 11KV having Consumer ID : 942304500 at the premises at Anandapur, Saltora water supply scheme(Intake), Bankura. |  |  | BILL/00956/2024-2025 | BP-2024-25-237 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.17 | 0 | 0 | 0
19 | BANKURA |  | Bankura Mechanical | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Upward revision of contract Demand from 60KVA to 98 KVA at 11KV having Consumer ID : 942304600 at the premises at Biharinath, Saltora, Bankura. |  |  | BILL/00957/2024-2025 | BP-2024-25-238 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.71 | 0 | 0 | 0
20 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Laying of different dia DI (k9) rising main including all allied works for Augamentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000071/2022-2023 | 1698/BQA | 28/07/2022 | 01/01/2026 | GOUTAM BHATTACHRYYA | 87.82 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Soil Investigation work for construction of OHR (550 CUM CAPACITY) under Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte (Zone- II) (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000642/2022-2023 | 581/BQA | 17/03/2023 | 02/10/2025 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 0 | 100
22 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Soil Investigation work for construction of CWR (250 CUM CAPACITY) under Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte. (Head Work Site) (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000643/2022-2023 | 582/BQA | 17/03/2023 | 01/10/2025 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 0 | 100
23 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Soil Investigation work for construction of OHR (250 CUM CAPACITY) under Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division, P.H.E. Dte (Zone- I) (2nd Call) | Assistant Engineer | Junior Engineer | ORD/000641/2022-2023 | 580/BQA | 17/03/2023 | 01/10/2025 | MS G. MITRA AND ASSOCIATES | 0.68 | 0 | 0 | 100
24 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | CONSTRUCTION, COMMISSIONING OF RCC OVERHEAD RESEVOR OF CAPACITY 550CUM AND STAGING HEIGHT 20 MTR. AS PER APPROVE DRAWING AND LAYING D.I(K-7) AND H.D.P.E PIPE LENGTH FOR DISTIBUTION SYSTEM INCLUDING PROVING FHTC FOR AUGMENTATION OF SUB-SURFACE WATER BASED WATER PIPE LINE SYSTEM FOR SALTORA PWSS.(FOR ZONE-II) | Assistant Engineer | Junior Engineer | ORD/000123/2023-2024 | 1257/BQA | 26/05/2023 | 17/12/2025 | DEBAKI RANJAN SARKAR | 647.6 | 0 | 0 | 0
25 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Construction and commission of R.C.C Over Head Reservoir of capacity 250 cum and staging height 20 mtr as per approved drawing & Laying DI (K7) & HDPE pipe line for distribution system including Providing FHTC for Augmentation of sub Surface Water Based Water Supply scheme for Saltora PWSS under Bankura Sadar Sub Division of Bankura Division. PHE Dte. (For Zone -I) | Assistant Engineer | Junior Engineer | ORD/000113/2023-2024 | 1195/BQA | 22/05/2023 | 16/02/2024 | SIB SANKAR CHOWDHURY | 391.5 | 76.17 | 19.46 | 19
26 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Continuation for supply 01 (One) no. Diesel / LPG / CNG driven Luxury Taxi / Bolero / Scorpio / Innova on hire basis for inspection of JJM works across Bankura district of Deputy Superintending Engineer, PIU, WBDWSIP, PHE Dte. For the period from 01/04/2024 to 30/09/2024 (183 Days). | Assistant Engineer | Junior Engineer | ORD/001452/2023-2024 | 472\BSD | 28/03/2024 | 27/09/2024 | TARUN KUMAR BHATTACHARYYA | 0.87 | 2.31 | 265.43 | 0
27 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Construction of Pump House including plinth protection, Ramp etc. according to departmental design & drawing at Saltora Z-I OHR Site for Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS Under Satora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Z- I) | Assistant Engineer | Junior Engineer | ORD/001411/2024-2025 | 28/BQA | 02/01/2025 | 01/01/2026 | KABISH KUMAR GHOSH | 36.78 | 0 | 0 | 1
28 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Saltora PWSS for providing Functional household Tap Connection (FHTC). Block- Saltora, District- Bankura, West Bengal. | SM/10292 | Augmentation | Construction of Pump House including plinth protection, Ramp etc. according to departmental design & drawing at Anandapur Intake Site for Augmentation of Sub Surface Water Based Water Supply Scheme for Saltora PWSS Under Satora Block under Bankura Sadar Sub-Division of Bankura Division, PHE Dte. (Intake Site) | Assistant Engineer |  | ORD/000068/2025-2026 | 1008/BQA | 25/04/2025 | 24/07/2025 | GOUTAM GHOSH | 32.15 | 0 | 0 | 0
Total | [13 empty] | 1940.84 | 447.53 | 23.06