## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 300 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Jhantipahari and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. (Zone- I) |  | Junior Engineer | ORD/000236/2022-2023 | 362/BSD | 13/04/2022 | 28/04/2022 | MABCO CONSULTANT | 1.85 | 1.85 | 100 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Soil Investigation work for Construction and commissioning of R.C.C Over Head Reservoir of capacity 250 cum and staging height 20 mtr for Augmentation of piped water supply scheme for Jhantipahari and its adjoining mouzas (JJM REVISION) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. (Zone- II) | Assistant Engineer |  | ORD/001102/2022-2023 | 361\BSD | 13/04/2022 | 28/04/2022 | MOYTEC | 1.85 | 1.85 | 100 | 100
3 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000024/2022-2023 | 2036/BQA | 29/09/2022 | 29/09/2022 | Resource Division | 0.05 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 305.79 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | rail bhoomi crossing seva |  |  | BILL/00914/2023-2024 | FHTC/09 | 01/09/2023 | 01/09/2023 | SOUTH EASTERN RAILWAY | 1.06 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Construction of 300 m³ capacity R.C.C OHR (based on Departmental Design Ref. Drawing No. PC- I/O.H.R./7/2012 (Sheet 1 &2)with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. and allied works for Augmentation of JHANTIPAHARI W/S Scheme (Zone - I) under Bankura Divn, PHE Dte. (Part - A), and HDPE pipe line for distribution system with FHTC for the proposed Augmentation of Jhantipahari piped W/S Scheme (Zone - I) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000205/2022-2023 | 1970/BQA | 22/09/2022 | 31/03/2026 | M/S TARUN KUMAR PATRA | 328.26 | 286.87 | 87.39 | 73
7 | BANKURA |  | Bankura Mechanical | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Formal work order for the work of Providing and installation of High lift & Low Lift pumping machineries and other electromechanical accessories for Augmentation of sub Surface water base water supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block under Bankura Mechanical Division PHE Dte, Dist :Bankura under JJM. | Assistant Engineer | Junior Engineer | ORD/000487/2023-2024 | 1818/BMD | 09/08/2023 | 05/02/2024 | EASTERN INDIA SALES & SERVICE | 176.93 | 116.89 | 66.06 | 45
8 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Balance allied works of Augmentation of Sub-Surface Based Water Supply Scheme for Jhantipahari (Zone-I) under Bankura Sadar Sub-Division of BANKURA Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000169/2024-2025 | 1809/BQA | 11/07/2024 | 08/11/2024 | M/S TARUN KUMAR PATRA | 191.18 | 133.47 | 69.81 | 60
9 | BANKURA |  | Bankura Mechanical | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Upward revision of contract Demand from 100KVA to 138 KVA at 11KV having Consumer ID : 942304300 at the premises at Jhantipahari water supply scheme(Intake), Jhantipahari, Bankura. |  |  | BILL/00958/2024-2025 | BP-2024-25-236 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.23 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Construction of 250 m³ capacity R.C.C OHR (based on Departmental Design Ref. Drawing No. PC- I/O.H.R./7/2012 (Sheet 1 &2)with 20 mtr. staging height including foundation, pipeline connection and cost of pipes , specials etc. and allied works for Augmentation of JHANTIPAHARI W/S Scheme (Zone - II) under Bankura Divn, PHE Dte. (Part - A), and HDPE pipe line for distribution system with FHTC for the proposed Augmentation of Jhantipahari piped W/S Scheme (Zone - II) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. (Part - B) | Assistant Engineer | Junior Engineer | ORD/000209/2022-2023 | 1971/BQA | 22/09/2022 | 01/04/2026 | GOPAL CHANDRA CHOWDHURY | 393.86 | 316.91 | 80.46 | 80
11 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Augmentation of Jhantipahari piped W/S Scheme (Zone - I) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000435/2023-2024 | 2269/BQA | 01/08/2023 | 01/04/2026 | M/S TARUN KUMAR PATRA | 153.91 | 0 | 0 | 82
12 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Construction of high lift pump house, construction of guard room and toilet and construction of WBSEDCL room at Jhantipahari water supply scheme (Zone - I) under Augmentation of Sub-Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District:- Bankura. | Assistant Engineer | Junior Engineer | ORD/001382/2024-2025 | 20/BQA | 02/01/2025 | 01/07/2026 | SHYAMAL KUMAR DAS | 45.94 | 0 | 0 | 1
13 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Construction of Guard Room & Toilet & Boundary Wall of Augmentation of Jhantipahari piped W/S Scheme and adjoining mouzas under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/001410/2024-2025 | 27/BQA | 02/01/2025 | 02/04/2025 | BROTIN UPADHYAY | 25.89 | 0 | 0 | 0
14 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Balance allied works of Augmentation of Sub-Surface Based Water Supply Scheme for Jhantipahari (Zone-II) under Bankura Sub-Division of BANKURA Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000175/2024-2025 | 1812/BQA | 11/07/2024 | 01/01/2026 | GOPAL CHANDRA CHOWDHURY | 129.15 | 0 | 0 | 6
15 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Sinking of 01 no. 200 mm dia. Horizontal River Bed Tube Well with fitting of 200 mm dia. strainer with of collecting line in river DARAKESHWAR under Augmentation of Jhantipahari water supply scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (Zone- II) | Assistant Engineer |  | ORD/000151/2025-2026 | 1304/BQA | 17/06/2025 | 01/08/2025 | COSMIC CONSTRUCTION | 8.96 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Crossing Rail Track ( South Eastern RLY. K.M. 252/1 -3) in between Jhantipahari Rly. Station (JPH) & Chhatna Rly. station (CJN) , P.S.Chhatna ,by Jack Pushing method with 300 mm (OD) Spirally welded MS Casing Pipe with 100 mm dia. MS carrier pipe under Augmentation of Jhantipahari piped Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001951/2024-2025 | 681/BQA | 12/03/2025 | 11/05/2025 | GOPAL CHANDRA CHOWDHURY | 33.25 | 0 | 0 | 100
17 | BANKURA |  | Bankura Division | Augmentation of Sub- Surface Water Based Water Supply Scheme for Jhantipahari to accommodate FHTC in Chhatna Block, District- Bankura. Block- Chhatna, District- Bankura, West Bengal. | SM/10293 | Augmentation | Bill for Road restoration Jhantipahari Kashipur Road from CH:0.060 KM to 0.76 KM permanent Restoration of road for the purpose of laying UPVC pipe line along and across of Jhantipahari High school- Chhatna Saltora Road |  |  | BILL/00108/2026-2027 |  | 09/04/2026 | 09/04/2026 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 59.37 | 0 | 0 | 0
Total | [13 empty] | 1859.54 | 857.83 | 46.13