## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Work Order for Preparation of Detailed Project Report for Augmentation of Simlapal Piped Water Supply Scheme, Block : Simlapal, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) |  | Junior Engineer | ORD/000528/2021-2022 | 668/KSD | 24/09/2021 | 14/10/2021 | LEMNISCATE | 3.76 | 3.67 | 97.53 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Work Order for Soil Investigation work for the proposed construction of RCC Over Head Reservoir of capacity 400 CuM, stagging height 20.00 Mtr. for Augmentation of Simlapal water supply scheme (JJM) under Khatra Sub- Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) |  | Junior Engineer | ORD/000101/2022-2023 | 132/KSD | 21/04/2022 | 06/05/2022 | M/S JAI KISHAN AGRO SCIENCE | 1.85 | 1.85 | 100 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000028/2022-2023 | 2282/BQA | 30/11/2022 | 30/11/2022 | Resource Division | 80.24 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Construction of High lift Pump House / Panel Room / Sub-Station building with sanitary & water supply arrangement and Sinking of 1 (One) No. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Augmentation of Simlapal Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000549/2022-2023 | 485/BQA | 13/03/2023 | 26/07/2023 | UTTAM KUMAR SINHAMAHAPATRA | 28.83 | 28.81 | 99.92 | 60
5 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Construction of High lift Pump House / Panel Room / Sub-Station building with sanitary & water supply arrangement and Sinking of 1 (One) No. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Augmentation of Simlapal Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000550/2022-2023 | 486/BQA | 13/03/2023 | 29/03/2024 | M/S SUPRIYA CHATTERJEE | 28.8 | 28.79 | 99.95 | 65
6 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Construction of Boundary Wall with allied Works at Head Work site for Augmentation of Simlapal Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000551/2022-2023 | 491/BQA | 13/03/2023 | 27/04/2023 | GOUTAM MUKHERJEE | 27.05 | 16.55 | 61.19 | 60
7 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal under Khatra Sub division under Bankura Division, PHE Dte. Location of site: (1) Near Simlapal Party Office, (2) Near Simlapal Sabji Market & (3) Near Simlapal PWD Office. | Assistant Engineer | Junior Engineer | ORD/000879/2023-2024 | 3007/BQA | 03/11/2023 | 16/04/2024 | M/S TARUN KUMAR PATRA | 20.46 | 19.5 | 95.29 | 90
8 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | New service connection at Simlapal CWR-II & OHR site of Simlapal piped water supply scheme of Simlapal block under Bankura Division PHE Dte. |  |  | BILL/00713/2024-2025 | BP-243/2024-25 | 28/08/2024 | 28/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 2.01 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Load extended service connection at CWR Site of Simlapal Piped Water Supply Scheme (Consumer Id-942308000) of Simlapal Block under Bankura Division,PHE Dte. |  |  | BILL/00985/2024-2025 | BP-326/2024-25 | 27/09/2024 | 27/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 3.6 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline of distribution system with allied works and providing ¿FHTC (Functional House Hold Tap Connection)¿ for Augmentation of Simlapal Piped Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Total House Hold - 3489 Nos.) | Assistant Engineer | Junior Engineer | ORD/000241/2022-2023 | 2112/BQA | 03/11/2022 | 02/04/2025 | M/S TARUN KUMAR PATRA | 366.97 | 294.07 | 80.14 | 80
11 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Supplying, laying, fitting, fixing and jointing of HDPE pipeline at different mouzas for Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿of Augmentation of Simlapal PWSS Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000023/2023-2024 | 827/BQA | 17/04/2023 | 31/07/2025 | M/S TARUN KUMAR PATRA | 49.22 | 47.8 | 97.13 | 95
12 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Construction of 400 Cum. Capacity R.C.C. OHR (based on Departmental Design) with 20 mtr. staging height and Sinking of 4 (Four) Nos. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Augmentation of Simlapal Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000105/2023-2024 | 1188/BQA | 22/05/2023 | 01/01/2025 | SIB SANKAR CHOWDHURY | 183.3 | 114.97 | 62.72 | 80
13 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Construction and commissioning of Clear Water Reservoir (100 CUM Capacity) at Over Head Reservoir site and Sinking of 1 (One) No. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Augmentation of Simlapal Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000468/2022-2023 | 283/BQA | 13/02/2023 | 03/02/2025 | SUBHADIP KOLEY | 34.03 | 29.02 | 85.28 | 50
14 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Construction and commissioning of Clear Water Reservoir (100 CUM Capacity) at Over Head Reservoir site and Sinking of 1 (One) No. 200 mm dia. X 4.50 Mtr. depth horizontal river bed tube well, using MS "T" and Laying, Fitting & fixing 100 mm G.I. collecting line from river bed tube well to CWR with allied works for Augmentation of Simlapal Water Supply Scheme (JJM) under Khatra Sub-Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000469/2022-2023 | 284/BQA | 13/02/2023 | 11/12/2026 | SAIKAT CHOWDHURY | 34.03 | 26.42 | 77.64 | 60
15 | BANKURA |  | Bankura Division | Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal. | SM/10294 | Augmentation | Construction of Office Cum Operater room and room for WBSEDCLwith allied works for Augmentation of Simlapal PWSS for providing Functional household Tap Connection (FHTC), Block- Simlapal, District- Bankura, West Bengal under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000346/2024-2025 | 2340/BQA | 09/09/2024 | 11/01/2025 | UTTAM KUMAR SINHAMAHAPATRA | 10.54 | 10.03 | 95.14 | 90
Total | [13 empty] | 874.69 | 621.47 | 71.05