## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Laying districution system using different dia D.I K7 pipes for improvement of Khatra - Ranibandh-Hirbandh water supply scheme under BRGF ph - 1 under Bankura Division PHE Dte. Zone - K Sl no - 04 |  |  | VCH/002902/2021-2022 | FHTC/17 | 17/03/2022 | 17/03/2022 | GOPAL CHANDRA CHOWDHURY | 11.88 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Laying extra HDPE pipe lineto cover Budhkhila (60) mouzas for construction and commissioning of FHTC (Funtional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of by Zone- J (Rudra ) to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. sl no - 19 |  |  | VCH/002857/2021-2022 | IMP/K-R-H | 15/03/2022 | 15/03/2022 | GOPAL CHANDRA CHOWDHURY | 4.7 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Supply of M.S pipe for laying the sa,e during HDD boring including cutting, welding and other allied works for road crossing in connection with the work of Improvement to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) block - Ranibandh under Khatra Sub - Division of Bankura Division, PHE Dte. zone - M2 sl no - 18 |  |  | VCH/002858/2021-2022 | IMP/K-R-H | 15/03/2022 | 15/03/2022 | DEBAKI RANJAN SARKAR | 3.38 | 0 | 0 | 0
4 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Biradihi (39) & Diktor (40) mouzas by retrofitting Zone-C (Biradihi) of Khatra-Hirbandh-Ranibandh Water Supply Scheme (BRGF Ph-I) at Block- Hirbandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  |  | VCH/002856/2021-2022 | IMP/K-R-H | 15/03/2022 | 15/03/2022 | PARTHA PRATIM CHHATAIT | 23.59 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Making HDD (Horizontal directional) bore & laying of various size casing pipes/water main inside HDD bore in rocky zone area ......including cutting the driving & receiving pit as per required size for crossing the national /..............using various machineries such as crane, jack, jacking materials, pushing jack technology .performing the work including mobilization charge of machneries required fro performing the work as per direction of the EIC conncetion with Improvement to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. zone - M2 sl no - 17 |  |  | VCH/002860/2021-2022 | IMP/K-R-H | 15/03/2022 | 15/03/2022 | DEBAKI RANJAN SARKAR | 3.71 | 0 | 0 | 0
6 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Making HDD (Horizontal directional) bore & laying of various size casing pipes/water main inside HDD bore in rocky zone area ......including cutting the driving & receiving pit as per required size for crossing the national /..............using various machineries such as crane, jack, jacking materials, pushing jack technology .performing the work including mobilization charge of machneries required fro performing the work as per direction of the EIC conncetion with Improvement to Khatra - Hirbandh-Ranibandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. zone - M2 sl no - 16 |  |  | VCH/002859/2021-2022 | IMP/K-R-H | 15/03/2022 | 15/03/2022 | DEBAKI RANJAN SARKAR | 3.93 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Laying distribution system using different dia D.I - K 7 pipes for improvement of Khatra-Ranibandh-Hirbandh W/S Scheme (BRGF ph - I project) under Khatra Sub - Division of Bankura Division, PHE Dte. Zone - M1 sl no - 01 |  |  | VCH/002861/2021-2022 | IMP/K-R-H | 15/03/2022 | 15/03/2022 | KONAR CONSTRUCTION | 58.1 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | 1st Ad-interim Payment against F/F bill for the work :- Improvement of Khatra, Ranibandh-Hirbandh works supply scheme under BRGF (PH-I) |  |  | VCH/002855/2021-2022 | IMP/K-R-H | 11/03/2022 | 11/03/2022 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 500 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Balance work of construction of boundary wall including construction of Path way at Over Head Reservoir Site for for Improvement of Khatra - Ranibandh - Hirbandh water supply scheme under BRGF (Phase - I) under Bankura Division, P.H.E. Dte. (Zone-Ashatara, Distance 48 Km. from Bankura) (Length -130 Mtr, No of Columns=38 Nos. Centre to Centre-3.5 Mtr.) For Single Tie Beam. | Assistant Engineer |  | ORD/000581/2022-2023 | 498/BQA | 13/03/2023 | 27/04/2023 | MD. AFSAR ALI | 14.25 | 0 | 0 | 0
10 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/07/2022 to 31/12/2022. |  | Junior Engineer | ORD/000750/2022-2023 | 234/KSD | 29/06/2022 | 30/12/2022 | BISWAJIT LAI | 0.87 | 0 | 0 | 50
11 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Javi (69), Bagdiha (70), Ledapakur (120), Mahadebsinan (121), Barapacha (123), Khata-Am (124), Raygar (125), Goalmuri (152), Sutan (153), Bhulagara (154), Dhankura (159) & Dhanjhar (164) mouzas by retrofitting Zone- M2 of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000623/2023-2024 | 2533/BQA | 08/09/2023 | 23/10/2023 | GANESH ROY | 36.75 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Crossing road by 200 mm dia MS pipe by Jack pushing method, interconnection of Rising Main (Zone-M1 & M2) with pumping main, laying & fabrication of MS pipe in another 3 (Three) Nos. places with all allied works for balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000024/2023-2024 | 828/BQA | 17/04/2023 | 17/05/2023 | M/S TARUN KUMAR PATRA | 12.53 | 0 | 0 | 100
13 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01/11/2022 to 31/01/2023. | Assistant Engineer |  | ORD/001114/2022-2023 | 390/KSD | 28/10/2022 | 28/01/2023 | SRIKANTA MONDAL | 0.44 | 0 | 0 | 20
14 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000002/2022-2023 | 1708/BQA | 29/07/2022 | 29/07/2022 | Resource Division | 155.57 | 0 | 0 | 0
15 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 182.72 | 0 | 0 | 0
16 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Purchase of land for proposed 02 Nos. of OHR for Improvement of khatra-Hirbandh-Ranibandh w/s scheme under BRGF (Phase - I) |  |  | BILL/00031/2022-2023 |  | 30/11/2022 | 30/11/2022 | SWAJALDHARA PROJECT, BANKURA ZILLA PARISAD. | 22.6 | 0 | 0 | 0
17 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01.05.2023 to 31.07.2023. | Assistant Engineer |  | ORD/000170/2023-2024 | 85/KSD | 24/04/2023 | 25/07/2023 | SRIKANTA MONDAL | 0.44 | 0 | 0 | 50
18 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Continuation Work order for Supply of 1 (One) No. Diesel/LPG/CNG driven Motor Cab (Luxury Taxi) on hire basis for Office of the Assistant Engineer, Khatra Sub-Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. for the period from 01/07/2023 to 31/12/2023. | Assistant Engineer | Junior Engineer | ORD/000422/2023-2024 | 161/KSD | 30/06/2023 | 31/12/2023 | BISWAJIT LAI | 0.87 | 0 | 0 | 40
19 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Continuation Work Order for Supply of 1 (One) No. Diesel/LPG/CNG driven Luxury Taxi/ Bolero/ Scorpio on hire basis for Office of the Executive Engineer, Bankura Division, P.H.E. Dte. for the Period from 01.08.2023 to 31.10.2023. | Assistant Engineer | Junior Engineer | ORD/000494/2023-2024 | 217/KSD | 31/07/2023 | 31/10/2023 | SRIKANTA MONDAL | 0.44 | 0 | 0 | 40
20 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Construction of 200 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height, Construction of Chlorine Room and Construction of Operator cum Guard Room of Ashatora (Zone-CE) under balance work of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001338/2024-2025 | 3163/BQA | 24/12/2024 | 24/03/2025 | SUBHANKAR BANERJEE | 90.99 | 0 | 0 | 0
21 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Construction of 200 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height, Construction of Chlorine Room and Construction of Operator cum Guard Room of Zone-M2 under balance work of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/001339/2024-2025 | 3164/BQA | 24/12/2024 | 24/03/2025 | S B ASSOCIATES | 91.37 | 0 | 0 | 0
22 | BANKURA |  | Bankura Mechanical | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Formal work order for the work of Providing And Installation Of Pumping Machineries, Substation Equipments And Other Electro-Mechanical Accessories at Head Works site for Improvement of Khatra-Ranibandh-Hirbandh Water supply Scheme, Block- Ranibandh, Dist- Bankura under Bankura Mechanical Division, PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/001000/2020-2021 | 1319/BMD | 18/11/2020 | 18/05/2021 | DEY ENTERPRISE | 107.65 | 0 | 0 | 95
23 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Work Order for Supply, Delivery and Stacking of C.I.D.F. Sluice Valve of under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) | Assistant Engineer | Junior Engineer | ORD/001300/2023-2024 | 323\KSD | 10/11/2023 | 25/11/2023 | SSPR VALVE MANUFACTURING PVT. LTD. | 1 | 0 | 0 | 100
24 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000156/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 15.54 | 0 | 0 | 0
25 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Javi (69), Bagdiha (70), Ledapakur (120), Mahadebsinan (121), Barapacha (123), Khata-Am (124), Raygar (125), Goalmuri (152), Sutan (153), Bhulagara (154), Dhankura (159) & Dhanjhar (164) mouzas by retrofitting Zone- M2 of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme under BRGF (Phase - I) at Block- Ranibandh, Dist.- Bankura under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. ( Total FHTC- 1033) No of FHTC- 517 ( PART-B ) | Assistant Engineer | Junior Engineer | ORD/000091/2023-2024 | 2534/BQA | 08/09/2023 | 01/04/2026 | MUNMUN UPADHYAY | 36.75 | 0 | 0 | 0
26 | BANKURA |  | Bankura Division | Laying distribution system, rising main, construction of OHR and boundary wall including provision of FHTC under balance work of Improvement of Khatra-Ranibandh-Hirbandh Water Supply Scheme under Jal Swapna & Jal Jeevan Mission Programme. | SM/10295 | Augmentation | Construction of 250 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height, Construction of Chlorine Room and Construction of Operator cum Guard Room of Zone-M1 under balance work of Improvement of Khatra - Ranibandh - Hirbandh Water Supply Scheme (BRGF Ph - I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001340/2024-2025 | 3165/BQA | 24/12/2024 | 24/03/2025 | SUBHENDU SEKHAR GORAI | 92.86 | 0 | 0 | 5
Total | [13 empty] | 1472.94 | 0 | 0