## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000027/2022-2023 | 2283/BQA | 30/11/2022 | 30/11/2022 | Resource Division | 1250.64 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Construction of R.C.C. Clear water reservoir (C.W.R.) of capacity 200 M3 for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer |  | ORD/000470/2022-2023 | 285/BQA | 13/02/2023 | 14/05/2023 | ASOKE KUMAR SAHU | 29.63 | 0 | 0 | 30
3 | BANKURA |  | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Construction of High lift Pump House cum Panel Room cum Sub-Station building with sanitary & water supply arrangement for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000552/2022-2023 | 492/BQA | 13/03/2023 | 11/06/2023 | SUBHENDU SEKHAR GORAI | 25.87 | 0 | 0 | 5
4 | BANKURA |  | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Construction of Chlorine Room at Head Work Site for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000567/2022-2023 | 493/BQA | 13/03/2023 | 11/06/2023 | M/S S.M ENTERPRISE | 4.7 | 0 | 0 | 100
5 | BANKURA |  | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Construction of Operator cum Guard Room with water supply and sanitary arrangement for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000573/2022-2023 | 494/BQA | 13/03/2023 | 11/06/2023 | KABISH KUMAR GHOSH | 5.52 | 0 | 0 | 100
6 | BANKURA |  | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Service connection charge for Shyamsundarpur (Zone IIA & IIB) water supply scheme at head works site Raipur block under BMD,PHE Dte.(SM/10296) |  |  | BILL/00349/2024-2025 | BP-146/2024-25 | 03/07/2024 | 03/07/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 8.92 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Construction of Boundary wall, Approach road, Land Development with other allied works for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. under Bankura Division, P.H.E. Dte. (For Head Work site) | Assistant Engineer | Junior Engineer | ORD/000575/2022-2023 | 495/BQA | 13/03/2023 | 02/04/2025 | D. S. ENTERPRISE | 29.02 | 0 | 0 | 82
8 | BANKURA |  | Bankura Mechanical | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Formal work order for the work of Providing and Installation of High Lift & Low Lift pumping machineries and other electro-mechanical accessories for Syamsundarpur (Zone-IIA & IIB) water supply scheme under Raipur water supply scheme (BRGF Ph-I) under JJM Programme under Bankura Mechanical Division PHE Dte. Block-Raipur, Dist-Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000248/2023-2024 | 951/BMD | 17/05/2023 | 29/09/2025 | R.N.S. TRADING | 276.53 | 0 | 0 | 32
9 | BANKURA |  | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Sinking of 12 (Twelve) Nos. 200 mm dia. X 6.50 Mtr. depth horizontal river bed tube well, using MS "T", MS delivery main collecting line from river bed tube well to CWR incuding supply and erecting of guard piling etc. all complete, laying rising main using different dia D.I. - K9 pipes and providing ¿FHTC (Functional House Hold Tap Connection)¿ with all allied works for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division P.H.E. Dte. (Total Household : 5110 Nos.) | Assistant Engineer | Junior Engineer | ORD/000240/2022-2023 | 2111/BQA | 03/11/2022 | 01/04/2026 | GOPAL CHANDRA CHOWDHURY | 740.81 | 0 | 0 | 60
10 | BANKURA |  | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Construction of Sub-Station Building with all allied works for balance work of Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001144/2023-2024 | 346/BQA | 05/02/2024 | 01/04/2025 | GANGADHAR MONDAL | 18.99 | 0 | 0 | 83
11 | BANKURA |  | Bankura Division | Creation of source, laying of Rising Main, construction of Pump House, CWR, Chlorine Room and Boundary Wall including provision of FHTC for Shyamsundarpur (Zone-IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph I) under Jal Swapna | SM/10296 | Augmentation | Balance Work of Construction of High lift Pump House cum Panel Room cum Sub-Station building with sanitary & water supply arrangement for Shyamsundarpur (Zone- IIA & IIB) Water Supply Scheme under Raipur Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000064/2024-2025 | 1519/BQA | 19/06/2024 | 01/12/2025 | SUBHENDU SEKHAR GORAI | 19.03 | 0 | 0 | 81
Total | [13 empty] | 2409.68 | 0 | 0