## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Hirbandh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER HIRBANDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10856 | New | New Service connection at Mini Piped w/s scheme at village-Shyampur Po-Gourbazar under Bankura Mechanical Division PHE Dte. |  |  | BILL/00814/2023-2024 | FHTC/09 | 07/09/2023 |  | INDPUR CCC | 0.12 | 0 | 0 | 0
2 | BANKURA | Hirbandh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER HIRBANDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10856 | New | New service connection for Shyampur, Hatirampur Mini water supply scheme under Bankura Division PHE DTE. |  |  | BILL/00155/2024-2025 | null | 16/05/2024 |  | HIRBANDH CCC | 0.11 | 0 | 0 | null
3 | BANKURA | Hirbandh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER HIRBANDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10856 | New | New service connection for Shyampur, Hatirampur Mini water supply scheme under Bankura Division PHE DTE. |  |  | BILL/00174/2024-2025 | BP-85/2024-25 | 29/05/2024 |  | HIRBANDH CCC | 0.11 | 0 | 0 | null
4 | BANKURA | Hirbandh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR SHYAMPUR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER HIRBANDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10856 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
Total | [13 empty] | 15500.96 | 0 | 0