## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Indpur | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KURCHIBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10884 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 25.5 | 0.16 | 48
2 | BANKURA | Indpur | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KURCHIBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10884 | New | Quotation bill for Kuchibedia, Jorda |  |  | BILL/00521/2022-2023 | Elec03 | 15/03/2023 | 15/03/2023 | INDPUR CCC | 0.12 | 0 | 0 | 0
3 | BANKURA | Indpur | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KURCHIBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10884 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/00381/2024-2025 |  | 03/07/2024 | 03/07/2024 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
4 | BANKURA | Indpur | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KURCHIBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10884 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 08/08/2024 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
5 | BANKURA | Indpur | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KURCHIBEDYA VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER INDPUR BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10884 | New | WBSEDCL Quotation bill for Scheme code - SM/10884. |  |  | BILL/00772/2024-2025 | BP-436/2024-25 | 28/11/2024 | 28/11/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.02 | 0 | 0 | 0
Total | [13 empty] | 15903.71 | 25.5 | 0.16