## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Bankura-I | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10909 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 29 | 0.19 | 48
2 | BANKURA | Bankura-I | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10909 | New | Rajkumardanga, Bankura-I, 9330862734 |  |  | BILL/00764/2022-2023 | FHTC/06 | 02/06/2023 | 02/06/2023 | LALBAZAR CCC | 0.12 | 0 | 0 | 0
3 | BANKURA | Bankura-I | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10909 | New | New service connection for "Kamlagora" Mini water supply scheme under Bankura Division PHE DTE. |  |  | BILL/00075/2024-2025 |  | 26/04/2024 | 26/04/2024 | CHHATNA CCC | 0.11 | 0 | 0 | 0
4 | BANKURA | Bankura-I | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10909 | New | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE (Kamlagora) HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. |  |  | BILL/00125/2024-2025 | BP-77/2024-25 | 22/05/2024 | 22/05/2024 | CHHATNA CCC | 0.11 | 0 | 0 | 0
5 | BANKURA | Bankura-I | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10909 | New | New service connection for Kamlagora water supply scheme(SVS) under BMD PHE Dte.(SM/10909) |  |  | BILL/01403/2024-2025 | BP/449/2024-25 | 09/01/2025 | 09/01/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.11 | 0 | 0 | 0
6 | BANKURA | Bankura-I | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR RAJ KUMAR VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER BANKURA- I BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10909 | New | Quotation asper WBSEDCL for SM/10909 |  |  | BILL/00909/2024-2025 | BP/455/2024-25 | 21/02/2025 | 21/02/2025 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0 | 0
Total | [13 empty] | 15501.2 | 29 | 0.19