## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Gangajalghati,Simlapal | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BELARMARI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10927 | New | Quotation of WBSEDCL for the scheme of SM /10927 |  |  | BILL/00852/2024-2025 | BP-289/2024-25 | 13/09/2024 | 13/09/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 0.12 | 0 | 0 | 0
2 | BANKURA | Gangajalghati,Simlapal | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BELARMARI VILLAGE HAVING HOUSEHOLDS LESS THAN 100 UNDER GANGAJALGHATI BLOCK UNDER JAL SAPNA/ JJM PROGRAMME | SM/10927 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 43 | 0.28 | 48
Total | [13 empty] | 15500.73 | 43 | 0.28