## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Simlapal | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KANSACHORA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11066 | New | New Connection at Kansachora,Machatora,Block-Simlapal, PHE Dte. |  |  | BILL/00318/2023-2024 | FHTC/04 | 29/04/2024 | 29/04/2024 | SIMLAPAL CCC | 0.12 | 0 | 0 | 0
2 | BANKURA | Simlapal | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KANSACHORA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11066 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/00381/2024-2025 |  | 03/07/2024 | 03/07/2024 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
3 | BANKURA | Simlapal | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KANSACHORA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11066 | New | New service connection for Kansachora Mini water supply scheme under Bankura Division PHE DTE. |  |  | BILL/00133/2024-2025 | BP-77/2024-25 | 22/05/2024 | 22/05/2024 | SIMLAPAL CCC | 0.12 | 0 | 0 | 0
4 | BANKURA | Simlapal | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KANSACHORA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11066 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 08/08/2024 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
5 | BANKURA | Simlapal | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KANSACHORA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11066 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.5 | 0.08 | 48
6 | BANKURA | Simlapal | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR KANSACHORA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SIMLAPAL BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11066 | New | Work Order for Installation of scheme information board for different mini piped water supply scheme within Simlapal Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Kasachora Village (SM/11066), (2) Mini Piped Water Supply Scheme for Krishnabati Village (SM/11060), (3) Mini Piped Water Supply Scheme for Memouli Village (SM/11061), (4) Mini Piped Water Supply Scheme for Bagnada Village (SM/11059) and (5) Mini Piped Water Supply Scheme for Suknabaid Village (SM/11068) | Assistant Engineer | Junior Engineer | ORD/002003/2024-2025 | 203\KSD | 10/03/2025 | 20/03/2025 | PRADYUMNA KOLEY | 0.75 | 0 | 0 | 95
Total | [13 empty] | 15904.57 | 12.5 | 0.08