## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Taldangra | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JEMUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11081 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 16 | 0.1 | 48
2 | BANKURA | Taldangra | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JEMUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11081 | New | New Connection at Jemuya, Taldangra,Pin-722102 PHE Dte |  |  | BILL/00413/2023-2024 | FHTC/04 | 23/04/2024 | 23/04/2024 | TALDANGRA CCC | 0.12 | 0 | 0 | 0
3 | BANKURA | Taldangra | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR JEMUA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11081 | New | Work Order for Installation of scheme information board for different mini piped water supply scheme within Taldangra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Jemua Village (SM/11081), (2) Mini Piped Water Supply Scheme for Mahishakanali Village (SM/11083), (3) Mini Piped Water Supply Scheme for Sushunia Village (SM/11034), (4) Mini Piped Water Supply Scheme for Tilabai Village (SM/11035), (5) Mini Piped Water Supply Scheme for Ghagar Village (SM/11050) and (6) Mini Piped Water Supply Scheme for Nabagram Village (SM/11052) | Assistant Engineer | Junior Engineer (Contractual) | ORD/001997/2024-2025 | 197\KSD | 10/03/2025 | 20/03/2025 | PRADYUMNA KOLEY | 0.9 | 0 | 0 | 95
Total | [13 empty] | 15501.64 | 16 | 0.1