## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Indus,Kotulpur | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Belpuskarini, Total House Hold: 21) | SM/11108 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 31.5 | 0.2 | 48
2 | BANKURA | Indus,Kotulpur | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Belpuskarini, Total House Hold: 21) | SM/11108 | New | New connection of Kishorkona Jl No-115, Indus Block PHE Dte. |  |  | BILL/00841/2023-2024 | FHTC/09 | 07/09/2023 | 07/09/2023 | INDUS CCC | 0.12 | 0 | 0 | 0
3 | BANKURA | Indus,Kotulpur | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Belpuskarini, Total House Hold: 21) | SM/11108 | New | New connection of Mahamaya (colony) 51-III, Indus Block PHE Dte. |  |  | BILL/00840/2023-2024 | FHTC/09 | 07/09/2023 | 07/09/2023 | INDUS CCC | 0.12 | 0 | 0 | 0
4 | BANKURA | Indus,Kotulpur | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Belpuskarini, Total House Hold: 21) | SM/11108 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/00381/2024-2025 |  | 03/07/2024 | 03/07/2024 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
5 | BANKURA | Indus,Kotulpur | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Belpuskarini, Total House Hold: 21) | SM/11108 | New | New service connection for Kishorkona (Dighalgram) Mini water supply scheme under Bankura Division PHE DTE |  |  | BILL/00159/2024-2025 | BP-77/2024-25 | 22/05/2024 | 22/05/2024 | INDUS CCC | 0.11 | 0 | 0 | 0
6 | BANKURA | Indus,Kotulpur | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Belpuskarini, Total House Hold: 21) | SM/11108 | New | New service connection for Kishorkona (Dighalgram) Mini water supply scheme under Bankura Division PHE DTE |  |  | BILL/00130/2024-2025 |  | 16/05/2024 | 16/05/2024 | INDUS CCC | 0.11 | 0 | 0 | 0
7 | BANKURA | Indus,Kotulpur | Bankura Division | Mini Piped Water Supply Scheme (Maximum 100 Households) WITHIN BISHNUPUR SUB-DIVISION, DISTRICT- BANKURA. Block- Kotulpur (Village Name: Belpuskarini, Total House Hold: 21) | SM/11108 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 08/08/2024 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
Total | [13 empty] | 15904.04 | 31.5 | 0.2