## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Ranibundh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MURKUM CHHOTA TUNG VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11113 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 18 | 0.12 | 48
2 | BANKURA | Ranibundh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MURKUM CHHOTA TUNG VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11113 | New | Bmsd Phe Dte Murkum C/o Sudip Saha ,Murkum Chhota Tung |  |  | BILL/00046/2023-2024 | FHTC/08 | 04/08/2023 | 04/08/2023 | RANIBANDH CCC | 0.11 | 0 | 0 | 0
3 | BANKURA | Ranibundh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MURKUM CHHOTA TUNG VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11113 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 08/08/2024 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
4 | BANKURA | Ranibundh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MURKUM CHHOTA TUNG VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11113 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/00381/2024-2025 |  | 03/07/2024 | 03/07/2024 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
5 | BANKURA | Ranibundh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR MURKUM CHHOTA TUNG VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11113 | New | Work Order for Installation of scheme information board for different mini piped water supply scheme within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Dhanjhar Village (SM/11112), (2) Mini Piped Water Supply Scheme for Birbandh Village (SM/11111), (3) Mini Piped Water Supply Scheme for Murkum Choto Tung Village (SM/11113), (4) Mini Piped Water Supply Scheme for Phuljhor Village (SM/11027), (5) Mini Piped Water Supply Scheme for Banpukuria Village (SM/11029) and (6) Mini Piped Water Supply Scheme for Gholkuri Village (SM/11031) | Assistant Engineer |  | ORD/001991/2024-2025 | 191\KSD | 10/03/2025 | 20/03/2025 | S. B. CONSTRUCTION | 0.9 | 0 | 0 | 90
Total | [13 empty] | 15904.59 | 18 | 0.11