## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Ranibundh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11115 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/00381/2024-2025 |  | 03/07/2024 | 03/07/2024 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
2 | BANKURA | Ranibundh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11115 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 08/08/2024 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
3 | BANKURA | Ranibundh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11115 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 12.6 | 0.08 | 48
4 | BANKURA | Ranibundh | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BARAPACHA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER RANIBUNDH BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11115 | New | Work Order Installation of scheme information board for different mini piped water supply scheme within Ranibandh Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Barapacha Village (SM/11115), (2) Mini Piped Water Supply Scheme for Ledapakur Village (SM/11116), (3) Mini Piped Water Supply Scheme for Sutan Village (SM/11120), (4) Mini Piped Water Supply Scheme for Burisal Village (SM/11117), (5) Mini Piped Water Supply Scheme for Goalmuri Village (SM/11118) and (6) Mini Piped Water Supply Scheme for Kawatanga Village (SM/11109) | Assistant Engineer |  | ORD/001990/2024-2025 | 190\KSD | 10/03/2025 | 20/03/2025 | S. B. CONSTRUCTION | 0.9 | 0 | 0 | 90
Total | [13 empty] | 15904.48 | 12.6 | 0.08