## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sarenga | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALGUMA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11129 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 16 | 0.1 | 48
2 | BANKURA | Sarenga | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALGUMA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11129 | New | New Connection at Baliguma Block-Sarenga in connection with 431 mini PWSS under BMSD PHE Dte. |  |  | BILL/00273/2023-2024 | FHTC/06 | 07/06/2023 | 07/06/2023 | SARENGA CCC | 0.11 | 0 | 0 | 0
3 | BANKURA | Sarenga | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALGUMA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11129 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/01248/2024-2025 | BP-214/2024-25 | 08/08/2024 | 08/08/2024 | RMN INFRASTRUCTURES LIMITED | 399.21 | 0 | 0 | 0
4 | BANKURA | Sarenga | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALGUMA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11129 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna |  |  | BILL/00381/2024-2025 |  | 03/07/2024 | 03/07/2024 | RMN INFRASTRUCTURES LIMITED | 3.75 | 0 | 0 | 0
5 | BANKURA | Sarenga | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALGUMA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11129 | New | New service connection for Baliguma Mini water supply scheme under Bankura Division PHE DTE. |  |  | BILL/00182/2024-2025 | BP-85/2024-25 | 29/05/2024 | 29/05/2024 | SARENGA CCC | 0.12 | 0 | 0 | 0
6 | BANKURA | Sarenga | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR BALGUMA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER SARENGA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11129 | New | Work Order for Installation of scheme information board for different mini piped water supply scheme within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme: - (1) Mini Piped Water Supply Scheme for Balguma Village (SM/11129), (2) Mini Piped Water Supply Scheme for Dhepua Village (SM/11130) and (3) Mini Piped Water Supply Scheme for Raghunathpur Village (SM/11132) | Assistant Engineer | Junior Engineer | ORD/002001/2024-2025 | 201\KSD | 10/03/2025 | 20/03/2025 | PRADYUMNA KOLEY | 0.45 | 0 | 0 | 90
Total | [13 empty] | 15904.25 | 16 | 0.1