## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Taldangra | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DOMAKANDA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11203 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME in 431( Four Hundred Thirty One ) no. villages under different blocks having less than 100 households under Bankura District in connection with Jal Swapna. | Assistant Engineer | Junior Engineer | ORD/000037/2022-2023 | 1731/BQA | 03/08/2022 | 30/06/2024 | RMN INFRASTRUCTURES LIMITED | 15500.61 | 0 | 0 | 48
2 | BANKURA | Taldangra | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DOMAKANDA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11203 | New | New Connection at Domakonda, Taldangra Pin-722101 PHE Dte. |  |  | BILL/00443/2023-2024 | FHTC/04 | 23/04/2024 | 23/04/2024 | TALDANGRA CCC | 0.12 | 0 | 0 | 0
3 | BANKURA | Taldangra | Bankura Division | MINI PIPED WATER SUPPLY SCHEME FOR DOMAKANDA VILLAGE HAVING HOUSEHOLD LESS THAN 100 UNDER TALDANGRA BLOCK UNDER JAL SAPNA/ JJM PROGRAMME. | SM/11203 | New | Work Order for Installation of scheme information board for different mini piped water supply scheme within Taldangra Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. Name of Scheme:- (1) Mini Piped Water Supply Scheme for Painada Modarpur Village (SM/11036), (2) Mini Piped Water Supply Scheme for Resiagara Village (SM/11037), (3) Mini Piped Water Supply Scheme for Shyamsundarpur Village (SM/11038), (4) Mini Piped Water Supply Scheme for Dunduria Village (SM/11199), (5) Mini Piped Water Supply Scheme for Domakonda Village (SM/11203) and (6) Mini Piped Water Supply Scheme for Chenchurya Village (SM/11046). | Assistant Engineer | Junior Engineer (Contractual) | ORD/002000/2024-2025 | 200\KSD | 10/03/2025 | 20/03/2025 | SUBHADIP KOLE | 0.9 | 0 | 0 | 95
Total | [13 empty] | 15501.64 | 0 | 0