## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I Project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos, Baramasia & Mukundapur (PIRRAGARI | SM/11822 | Retrofitting | Retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA of CHERABASTA (Zone - K) under Bankura - I,II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. (SM/11822) | Assistant Engineer | Junior Engineer | ORD/000500/2022-2023 | 378/BQA | 23/02/2023 | 09/04/2023 | SANJOY MONDAL | 25.4 | 0 | 0 | 100
2 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I Project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos, Baramasia & Mukundapur (PIRRAGARI | SM/11822 | Retrofitting | Laying HDPE pipe line, valve chamber & Household tap connection (FHTC) at Mobarakpur village & Kadmaghati School & ICDS of CHERABASTA (Zone - K) & ARJUNPUR (Zone- N) under Bankura - I, II & Barjora Block W/S Scheme (BRGF ph - I project) under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000119/2023-2024 | 323/BSD | 06/04/2023 | 13/04/2023 | BAYEN CONSTRUCTION | 0.96 | 0 | 0 | 100
3 | BANKURA |  | Bankura Division | Construction & commissioning of FHTC by Retrofitting of completed and commissioned piped water supply scheme of Bankura - I, II & Barjora Block (BRGF Ph - I Project) under JAL SWAPNO & Jal Jeevan Mission (JJM) for 02 nos, Baramasia & Mukundapur (PIRRAGARI | SM/11822 | Retrofitting | Extra FHTC survey work of retrofitting works for creation of 'FHTC (Functional House Hold Tap Connection' in connection with Jal Jeevan Mission (JJM) and JAL SWAPNA for KHYERKANALI, CHERABASTA, CHATARKANALI, TELEBEDIA, ARJUNPUR, HORIALGORA, KENDBONI, SONAHAHA & BANKATI under Bankura- I, II & Barjora Block W/S Scheme (BRGF Ph- I Project) under Bankura Sadar Sub- Division of Bankura Division P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000103/2023-2024 | 326/BSD | 06/04/2023 | 05/06/2023 | TAPAS DEY | 0.87 | 0 | 0 | 100
Total | [13 empty] | 27.22 | 0 | 0