## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas of Rejuvenation of Sarberia water supply scheme (including left out BRGF Mouzas) Block - Chhatna, Dist - Bankura under Jal Swapna & Jal Jeevan Mission Programme. | SM/11823 | Retrofitting | Construction and Commissioning of 'FHTC (Funtional House Hold Tap Connection) in mouzas of Rejuvenation of SARBERIA W/S Scheme ( Zone-I) (including Left out BRGF Mouzas] Block - Chhatna, Dist.- Bankura under JAL SWAPNA & Jal Jeevan Mission programe under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000370/2023-2024 | 2032/BQA | 24/07/2023 | 30/12/2026 | M/S TARUN KUMAR PATRA | 356.78 | 0 | 0 | 46
2 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas of Rejuvenation of Sarberia water supply scheme (including left out BRGF Mouzas) Block - Chhatna, Dist - Bankura under Jal Swapna & Jal Jeevan Mission Programme. | SM/11823 | Retrofitting | Crossing Rail Track ( South Eastern RLY. K.:BG- 245/17-19) in between Jhantipahari Rly. Station (JPH) & Chhatna Rly. station (CJN) , P.S.Chhatna ,by Jack Pushing method with 400 mm (OD) Spirally welded MS Casing Pipe with 200 mm dia. MS carrier pipe under Augmentation of Sarberia & its adjoining mouzas Water Supply Scheme under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001967/2024-2025 | 687/BQA | 12/03/2025 | 11/05/2025 | M/S TARUN KUMAR PATRA | 73.54 | 0 | 0 | 1
3 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas of Rejuvenation of Sarberia water supply scheme (including left out BRGF Mouzas) Block - Chhatna, Dist - Bankura under Jal Swapna & Jal Jeevan Mission Programme. | SM/11823 | Retrofitting | Crossing Rail Track ( South Eastern RLY. K.M Bg-. 218-2 /4) in between Rly. Station Bankura (BQA) & Onda Gram (ODM) Rly. station in Salghata mouza, P.S. Bankura,by Jack Pushing method with 400 mm (OD) Spirally welded MS Casing Pipe with 200 mm dia. MS carrier pipe under Augmentation of Sub-Surface water based water supply scheme (Left out from BRGF Mouza) for Onda under Bankura Sadar Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001958/2024-2025 | 684/BQA | 12/03/2025 | 11/05/2025 | GOPAL CHANDRA CHOWDHURY | 59.97 | 0 | 0 | 100
Total | [13 empty] | 490.29 | 0 | 0