## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Construction and commissioning of FHTC (Functional House Hold Tap Connection) in mouzas of Rejuvenation of Sarberia water supply scheme (including left out BRGF Mouzas) Block - Chhatna, Dist - Bankura under Jal Swapna & Jal Jeevan Mission Programme. | SM/11823 | Retrofitting | Construction and Commissioning of 'FHTC (Funtional House Hold Tap Connection) in mouzas of Rejuvenation of SARBERIA W/S Scheme ( Zone-I) (including Left out BRGF Mouzas] Block - Chhatna, Dist.- Bankura under JAL SWAPNA & Jal Jeevan Mission programe under Bankura Sadar Sub - Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000370/2023-2024 | 2032/BQA | 24/07/2023 | 31/03/2026 | M/S TARUN KUMAR PATRA | 356.78 | 0 | 0 | 46
Total | [13 empty] | 356.78 | 0 | 0