## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | Work Order for Preparation of Detailed Project Report for Augmentation of Sarenga Piped Water Supply Scheme, Block : Sarenga, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 02) |  | Junior Engineer | ORD/000545/2021-2022 | 02/A/KSD | 06/01/2022 | 06/02/2022 | INDRANIL DUTTA & ASSOCIATES | 4.07 | 4.02 | 98.93 | 0
2 | BANKURA |  | Bankura Mechanical | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of High lift pumping machineries and other electromechanical accessories for sub-surface water base Sarenga piped water supply scheme Block-Sarenga Dist -Bankura under Bankura Mechanical Division PHE Dte. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000304/2023-2024 | 1407/BMD | 18/07/2023 | 16/09/2023 | TAPAN KUMAR SARKAR | 55.92 | 40.62 | 72.63 | 15
3 | BANKURA |  | Bankura Division | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | Laying of DI (K7) pipe and supplying, laying, fitting, fixing, jointing of HDPE (Materials grade PE-100, PN-6) pipes for distribution system along with providing ¿FHTC (Functional House Hold Tap Connection)¿ and Laying Rising Main using D.I - K9 pipes and construction of R.C.C. Elevated Reservoir of capacity 450 cum and staging height 20.00 mtr. with allied work for Sub Surface water based Sarenga Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte | Assistant Engineer | Junior Engineer | ORD/000438/2023-2024 | 2272/BQA | 01/08/2023 | 02/07/2025 | PRINCE INDUTRIES (INDIA) | 640.53 | 381.01 | 59.48 | 84
4 | BANKURA |  | Bankura Division | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 23/04/2023 | P. K. TEWARY DRILLING CO | 8.41 | 0 | 0 | 99
5 | BANKURA |  | Bankura Division | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | Construction of Boundary wall, Approach road, Land Development with other allied works for Sub Surface water based Sarenga Piped Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000587/2022-2023 | 502/BQA | 13/03/2023 | 02/10/2024 | UTTAM KUMAR SINHAMAHAPATRA | 14.52 | 0 | 0 | 90
6 | BANKURA |  | Bankura Division | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 235.37 | 0 | 0 | 0
7 | BANKURA |  | Bankura Division | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | Laying of HDPE pipeline for Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000180/2024-2025 | 1892/BQA | 23/07/2024 | 02/07/2025 | PRINCE INDUSTRIES (INDIA) | 32.31 | 0 | 0 | 85
8 | BANKURA |  | Bankura Division | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000158/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 24.21 | 0 | 0 | 0
9 | BANKURA |  | Bankura Mechanical | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | New service connection for OHR site of Sarenga |  |  | BILL/00028/2024-2025 | BP-2024-25-38 | 10/05/2024 | 10/05/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.53 | 0 | 0 | 0
10 | BANKURA |  | Bankura Mechanical | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | New 3 Phase service connection for Sarenga OHR |  |  | BILL/00696/2024-2025 | BP-2024-25-187 | 13/08/2024 | 13/08/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.53 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | REVISED ESTIMATE FOR RESTORATION OF NEWLY CONSTRUCTED DAMAGED ROAD - " CHANDRAKONA-GOALTORE-SARENGA-SIMLIGHAT ROAD BETWEEN CHAINAGE 36+410 KM TO 36+678 KM ( RESTORATION OF FLEXIBLE PAVEMENT , CONCRETE PAVEMENT AND PCC SURFACE DRAIN ) FOR LAYING WATER PIPE LINE BY PHE DEPARTMENT UNDER BANKURA HIGHWAY DIVISION , P. W. (ROADS) DIRECTORATE IN THE DISTRICT OF BANKURA AND SIMLAPAL-SARENGA-BAMUNDIAGHAT ROAD BETWEEN CHAINAGE 19+999 KM TO 25.700 KM ( RESTORATION OF CONCRETE BLOCK(PAVER BLOCK) PAVEMENT / CONCRETE PAVEMENT ) FOR LAYING WATER PIPE LINE BY PHE DEPARTMENT UNDER BANKURA HIGHWAY DIVISION , P. W. (ROADS) DIRECTORATE IN THE DISTRICT OF BANKURA |  |  | BILL/01345/2024-2025 | BP-443/2024-25 | 11/12/2024 | 11/12/2024 | EXECUTIVE ENGINEER BANKURA HIGHWAY DIVISION | 92.53 | 0 | 0 | 0
12 | BANKURA |  | Bankura Division | Sub Surface water based Sarenga Piped water supply scheme, Block Sarenga under Khatra Sub-Division in Bankura District. | SM/11980 | Augmentation | Repair and Maintenance work of the Road from T01 to Asna under Sarenga Block in the District of Bankura , Vide Package No-Wb-03-239,Road Length-2.92 Km. (For Sub-Surface based Sarenga Piped Water supply scheme) |  |  | BILL/01641/2024-2025 | BP/483/2024-25 | 22/03/2025 | 22/03/2025 | EXECUTIVE ENGINEER & HPIU WBSRDA BISHNUPUR DIVISION | 2.52 | 0 | 0 | 0
Total | [13 empty] | 1125.44 | 425.65 | 37.82