## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | SM/12379 | Augmentation | Work Order for Preparation of Detailed Project Report for Augmentation of Chhoto Birbhanpur Piped Water Supply Scheme, Block : Sarenga, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 16) |  | Junior Engineer | ORD/000308/2022-2023 | 194/KSD | 24/05/2022 | 08/06/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 3.37 | 3.05 | 90.5 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | SM/12379 | Augmentation | Laying of DI (K7) pipe with supplying, laying, fitting, fixing, jointing of HDPE (Materials grade PE-100, PN-6) pipes for distribution system with ancillary works with providing ¿FHTC (Functional House Hold Tap Connection)¿, Laying Rising Main using different dia D.I. - K9 pipes and Construction of 200 m³ Capacity R.C.C OHR (based on Departmental Design) with 20 mtr. staging height including foundation, pipeline connection and cost of pipes, specials etc. and allied works for Augmentation for Chhoto - Birbhanpur Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000076/2023-2024 | 970/BQA | 28/04/2023 | 23/01/2024 | PARTHA PRATIM CHHATAIT | 289.03 | 167.43 | 57.93 | 60
3 | BANKURA |  | Bankura Mechanical | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | SM/12379 | Augmentation | Acceptance cum Formal work order for the work of Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chotobirbhanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sarenga Dist: Bankura. | Assistant Engineer,Driller-in-Charge | Junior Engineer | ORD/000188/2023-2024 | 964/BMD | 19/05/2023 | 18/04/2026 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 39.1 | 22.9 | 58.58 | 70
4 | BANKURA |  | Bankura Mechanical | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | SM/12379 | Augmentation | Acceptance cum Formal work order for the work of Name of Providing, & installation of Pumping machineries with other electro-mechanical accessories for Augmentation of Chotobirbhanpur piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sarenga Dist: Bankura. | Assistant Engineer |  | ORD/001353/2023-2024 | 1013/BMD | 22/05/2023 | 18/11/2023 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 47.59 | 0 | 0 | 0
5 | BANKURA |  | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | SM/12379 | Augmentation | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 23/04/2023 | P. K. TEWARY DRILLING CO | 8.41 | 0 | 0 | 99
6 | BANKURA |  | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | SM/12379 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 46.12 | 0 | 0 | 0
7 | BANKURA |  | Bankura Mechanical | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | SM/12379 | Augmentation | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC |  |  | BILL/00122/2023-2024 |  | 28/06/2023 | 28/06/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | SM/12379 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000161/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 6.82 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Ground water based piped water supply scheme for Chhota Birbhanpur & Adjoining Mouzas to Accommodate FHTC | SM/12379 | Augmentation | Work Order for Installation of scheme information board for 2 nos. site of Sub Surface water based Sarenga Piped Water Supply Scheme (SM/11980), 2 nos. site of Augmentation for Chhoto-Birbhanpur Water Supply Scheme (SM/12379) and 2 nos. site of Augmentation works for Chiltore and Its Adjoining mouzas Water Supply Scheme (SM/17725) within Sarenga Block under Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001917/2024-2025 | 161\KSD | 07/03/2025 | 17/03/2025 | SUBHADIP KOLE | 0.9 | 0 | 0 | 90
Total | [13 empty] | 442.34 | 193.39 | 43.72