## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | Work Order for Preparation of Detailed Project Report for Augmentation of Mukundapur Piped Water Supply Scheme, Block : Raipur, District : Bankura Under Jal Swapna Project under Khatra Sub-Division of Bankura Division, P.H.E. Dte. (Sl. No. 01) |  | Junior Engineer | ORD/000544/2021-2022 | 02/KSD | 06/01/2022 | 06/02/2022 | SIRCON ENGINEERING SERVICES | 3.61 | 0 | 0 | 0
2 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | Construction of Boundary Wall (Length- 130 Mtr.) with allied Works at Head Work site for Mukundapur and its adjoining mouzas Water Supply Scheme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000548/2022-2023 | 484/BQA | 13/03/2023 | 16/11/2025 | GOUTAM GHOSH | 19.46 | 0 | 0 | 0
3 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | Laying DI Pipe (K9) pipe, Construction of 1 No. 200 mm dia x 5.5 mtr. depth horizontal river bed tube well using MS "T " and Laying, Fitting & fixing 100 mm M.S. delivery main connecting line from river bed tube well to CWR for Augmentation of Mukundapur Water Supply Scheme under Khatra Sub-Division of Bankura Division , PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000547/2022-2023 | 483/BQA | 13/03/2023 | 01/04/2025 | GOUTAM GHOSH | 28.41 | 15.97 | 56.21 | 80
4 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | Supplying, laying, fitting, fixing, jointing of HDPE pipeline of distribution system with allied works, providing ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 150 Cum. Capacity R.C.C. OHR (based on Departmental Design) with 20 mtr. staging height with allied works for Augmentation of Mukundapur Water Supply Scheme under Khatra Sub-Division of Bankura Division , PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000107/2023-2024 | 1187/BQA | 22/05/2023 | 16/02/2024 | PARTHA PRATIM CHHATAIT | 384.93 | 176.75 | 45.92 | 45
5 | BANKURA |  | Bankura Mechanical | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | Acceptance cum Formal work order for the work of Providing and installation of pumping machineries and other electromechanical accessories for Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission program under Raipur Block in Bankura District under Bankura Division, PHE Dte. | Driller-in-Charge | Junior Engineer | ORD/000715/2023-2024 | 2172/BMD | 30/10/2023 | 16/06/2026 | DEY ENTERPRISE | 50.24 | 2.55 | 5.08 | 78
6 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | SOIL INVESTIGATION FOR PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN KHATRA SUB DIVITION OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000403/2022-2023 | 643/BQA | 24/03/2023 | 23/04/2023 | P. K. TEWARY DRILLING CO | 8.41 | 0 | 0 | 99
7 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000005/2023-2024 | 1120/BQA | 12/05/2023 | 12/05/2023 | Resource Division | 114.89 | 0 | 0 | 0
8 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000051/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 46.12 | 0 | 0 | 0
9 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000160/2023-2024 | 116/BQA | 10/01/2024 | 10/01/2024 | Resource Division | 7.76 | 0 | 0 | 0
10 | BANKURA |  | Bankura Mechanical | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. |  |  | BILL/01673/2023-2024 | BP-2023-24-186 | 22/03/2024 | 22/03/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.46 | 0 | 0 | 0
11 | BANKURA |  | Bankura Division | Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, PHE Dte. | SM/12380 | Augmentation | Crossing of Road at different location by Jack pushing method (600 mm dia RCC Hume pipes for casing pipe) for Distribution Main for Augmentation of Sub-Surface water Based piped water supply scheme for Mukundapur and adjoining Mouzas to accommodate FHTC under Jal Jeevan Mission programme under Raipur Block in Bankura District under Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/001388/2024-2025 | 35/BQA | 02/01/2025 | 16/02/2025 | PARTHA PRATIM CHHATAIT | 20.68 | 0 | 0 | 95
Total | [13 empty] | 688.96 | 195.27 | 28.34