## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Gargaria (Zone-A) under Sarenga Water Supply Scheme (BRGF Ph-I) due to damage done during strengthening-widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. | SM/12381 | Augmentation | Supplying, laying, fiting, fixing and jointing by DI (K9) for Rising Main & HDPE pipe for Distribution Main along with ancillary works due to damage done during Strengthening - Widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. under Water Supply Scheme for Gargaria (Zone-A) under Sarenga Water Supply Scheme (BRGF Ph-I) under Khatra Sub-Division of Bankura Division, P.H.E. Dte. |  | Junior Engineer | ORD/000386/2021-2022 | 162/BQA | 28/01/2022 | 27/02/2022 | EARTH MOVING (INDIA) | 88.36 | 73.87 | 83.6 | 0
2 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Gargaria (Zone-A) under Sarenga Water Supply Scheme (BRGF Ph-I) due to damage done during strengthening-widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. | SM/12381 | Augmentation | Laying extra HDPE pipeline,construction of different dia valve chambers & other allied works to increase pressure for Majuria (372), Makarkol (365), Jhukanala (366), Baispatra (367) & Deuli (369) mouzas by retrofitting of Water Supply Scheme for Gargarya, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Swapna & Jal Jeevan Mission Programme under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000664/2022-2023 | 508/BQA | 13/03/2023 | 27/04/2023 | UTTAM KUMAR SINHAMAHAPATRA | 2.48 | 2.32 | 93.56 | 60
3 | BANKURA |  | Bankura Division | Augmentation of water supply scheme for Gargaria (Zone-A) under Sarenga Water Supply Scheme (BRGF Ph-I) due to damage done during strengthening-widening of road from Pirorgari More to Brahamandiha by PWD (Roads) Dte. | SM/12381 | Augmentation | 300 mm X 200 mm X 300 m deep Tubewell by Rig boring method including interconnection with 100 mm dia. G.I. Pipe and Construction & commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ and Construction of 2 Nos. Pump Houses with ancillary works in different mouzas for Augmentation of Water Supply Scheme for Gargaria, Zone-A and its adjoining Mouzas under Sarenga Water Supply Scheme (BRGF Ph-I) under Jal Jeevan Mission under Khatra Sub-Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000369/2023-2024 | 2031/BQA | 24/07/2023 | 02/07/2025 | PRINCE INDUTRIES (INDIA) | 182.82 | 80.96 | 44.29 | 81
Total | [13 empty] | 273.66 | 157.15 | 57.42