## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA |  | Bankura Division | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. | SM/12382 | Augmentation | Sinking of 06 nos 200 mm dia. X 6.0 Mtr. depth Horizontal River Bed Tube Well including Supplying & Laying 100 mm dia MS connecting line including supply and Erecting of 40 mm dia G I Pipe for Guard pilling of 100 mm dia MS pipe from River bed T/W to Manifold at Kukrakuri intake site of Saltora- Chhatna W/S Scheme (BRGF ph - I project) of Bankura Division, PHE Dte. (Part-B) | Assistant Engineer |  | ORD/000247/2022-2023 | 2149/BQA | 14/11/2022 | 14/12/2022 | GOPAL CHANDRA CHOWDHURY | 85.9 | 71.36 | 83.08 | 0
2 | BANKURA |  | Bankura Division | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. | SM/12382 | Augmentation | Construction and commissioning of ¿FHTC (Functional House Hold Tap Connection)¿ in Bhadaspur Khas (10), Jahur Bana (102), Fatepur (103) & Amjhor (104) mouzas of Saltora Block including laying of 400 mm dia MS Rising main from manifold to CWR at Kukrakuri intake site of Saltora- Chhatna W/S Scheme (BRGF Ph - I Project) under Jal Jeevan Mission Programme under Bankura Division, P.H.E. Dte.Block - Saltora, No. of OHR:- 1No. No.of Mouza :- 4, Total House Hold- 258 Nos. | Assistant Engineer | Junior Engineer | ORD/000684/2022-2023 | 585/BQA | 20/03/2023 | 18/06/2023 | TAPAS KUMBHAKAR | 53.41 | 49.12 | 91.96 | 90
3 | BANKURA |  | Bankura Division | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. | SM/12382 | Augmentation | Construction of common manifold and Sinking of 03 nos 200 mm dia. X 6.0 Mtr. depth Horizontal River Bed Tube Well including Supplying & Laying 100 mm dia MS connecting line including supply and Erecting of 40 mm dia G I Pipe for Guard pilling of 100 mm dia MS pipe from River bed T/W to Manifold at Kukrakuri intake site of Saltora- Chhatna W/S Scheme (BRGF ph - I project) of Bankura Division, PHE Dte. | Assistant Engineer |  | ORD/000248/2022-2023 | 2150/BQA | 14/11/2022 | 29/12/2022 | SIB SANKAR CHOWDHURY | 42.96 | 42.74 | 99.49 | 20
4 | BANKURA |  | Bankura Mechanical | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. | SM/12382 | Augmentation | Formal work order for the work-Providing and Installation of Low lift pumping machineries and other electro-mechanical accessories for Augmentation of source by sinking of river bed Tube well including connecting line & M.S. Rising main at Kukrakuri in the river bed of Damodar and providing FHTC for Saltora Chhatna water supply scheme (BRGF Phase-I) under Jal Jeevan Mission under Bankura Mechanical Division PHE Dte. Dist-Bankura. | Assistant Engineer | Junior Engineer | ORD/000426/2022-2023 | 341/BMD | 03/03/2023 | 03/09/2023 | ORIENTAL ENGINEERING CO. | 99.53 | 89.03 | 89.44 | 100
5 | BANKURA |  | Bankura Division | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. | SM/12382 | Augmentation | Sinking of 06 nos 200 mm dia. X 6.0 Mtr. depth Horizontal River Bed Tube Well including Supplying & Laying 100 mm dia MS connecting line including supply and Erecting of 40 mm dia G I Pipe for Guard pilling of 100 mm dia MS pipe from River bed T/W to Manifold at Kukrakuri intake site of Saltora- Chhatna W/S Scheme (BRGF ph - I project) of Bankura Division, PHE Dte. (Part-A) | Assistant Engineer |  | ORD/000010/2022-2023 | 2148/BQA | 14/11/2022 | 14/12/2022 | M/S TARUN KUMAR PATRA | 85.81 | 72.26 | 84.21 | 100
6 | BANKURA |  | Bankura Division | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. | SM/12382 | Augmentation | Sinking of 04 (Four) nos. 200 mm dia. X 16.0 Mtr. depth Vertical River Bed Tube Well and supplying & laying of 150 mm dia MS collecting line with other allied works from riverbed to manifold at Kukhrakuri intake site of Saltora- Chhatna W/S Scheme (BRGF ph - I project) of Bankura Division, P.H.E. Dte. under Jal Swapna & Jal Jeevan Mission Programme. | Assistant Engineer | Junior Engineer | ORD/001463/2024-2025 | 84/BQA | 06/01/2025 | 20/05/2025 | SINGHA ENTERPRISE | 29.1 | 0 | 0 | 1
7 | BANKURA |  | Bankura Mechanical | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. | SM/12382 | Augmentation | Acceptance cum Formal work order for the work of Supply, Delivery and installation of Voltage Correction device and allied works for Augmentation of subsurface water based water supply scheme Saltora for providing FHTC in Saltora Block under Bankura Mechanical Division PHE Dte, Block: Saltora Dist :Bankura | Assistant Engineer | Junior Engineer | ORD/000339/2024-2025 | 784/BMD | 20/08/2024 | 17/04/2025 | DAS ENTERPRISE | 29.99 | 0 | 0 | 80
8 | BANKURA |  | Bankura Mechanical | Augmentation of source by sinking of Riverbed Tube Well, including connecting line & MS Rising main at Kukrakuri in the river of Damodar and providing FHTC for Saltora - Chhatna Water Supply Scheme (BRGF Phase -I) under Jal Jeevan Mission Programme. | SM/12382 | Augmentation | Acceptance cum Formal work order for the work of Providing, installation of Submersible Pumping machineries with other electro-mechanical accessories for 4 nos vertical tubewell at Intake Kukrakuri under Chhatna, Saltora Block Sub-Surface Water Based Piped Water Supply Scheme under Bankura Mechanical Division, P.H.E. Dte. Block: Saltora, Dist- Bankura | Assistant Engineer | Junior Engineer | ORD/000012/2025-2026 | 147/BMD | 30/04/2025 | 29/07/2025 | ORIENTAL ENGINEERING CO. | 27.6 | 0 | 0 | 100
Total | [13 empty] | 454.3 | 324.51 | 71.43