## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Mechanical | Rani Bandh Piped Water Supply Scheme | SM/12415 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Rani Bandh water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000163/2023-2024 | 875/BMD | 04/05/2023 | 31/10/2023 | TAPAN KUMAR SARKAR | 35.82 | 0 | 0 | 56
2 | BANKURA | Sonamukhi | Bankura Division | Rani Bandh Piped Water Supply Scheme | SM/12415 | New | Material Requisition To Resource Division |  |  | RTOR000080/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 79.07 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Division | Rani Bandh Piped Water Supply Scheme | SM/12415 | New | Material Requisition To Resource Division |  |  | RTOR000057/2023-2024 | 2523/BQA | 08/09/2023 | 08/09/2023 | Resource Division | 8.19 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Division | Rani Bandh Piped Water Supply Scheme | SM/12415 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR RANIBANDH PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000385/2023-2024 | 2045/BQA | 24/07/2023 | 01/04/2026 | PRINCE INDUTRIES (INDIA) | 587.96 | 0 | 0 | 73
5 | BANKURA | Sonamukhi | Bankura Division | Rani Bandh Piped Water Supply Scheme | SM/12415 | New | Balance Ancillary Work for ¿Ranibandh¿ and ¿Dhulai¿ Piped Water Supply Scheme, Sonamukhi Block, Bishnupur Sub Division under Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000424/2025-2026 | 1990/BQA | 16/09/2025 | 15/03/2026 | PRINCE INDUSTRIES (INDIA) | 194.43 | 0 | 0 | 15
Total | [13 empty] | 905.47 | 0 | 0