## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Mechanical | Bhat Pushkarini Piped Water Supply Scheme | SM/12416 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & TW No-II of Bhat Pushkarini piped water supply scheme under Bankura Mechanical Division, PHE Dte. Block : Sonamukhi , Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000114/2023-2024 | 772/BMD | 24/04/2023 | 21/10/2023 | PRADIP KUMAR DHABAL | 39.43 | 20.99 | 53.23 | 54
2 | BANKURA | Sonamukhi | Bankura Division | Bhat Pushkarini Piped Water Supply Scheme | SM/12416 | New | Material Requisition To Resource Division |  |  | RTOR000057/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 162.57 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Division | Bhat Pushkarini Piped Water Supply Scheme | SM/12416 | New | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 2942/BQA | 21/11/2024 | 21/11/2024 | Resource Division | 10.96 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Mechanical | Bhat Pushkarini Piped Water Supply Scheme | SM/12416 | New | Bhat Pushkarini Piped Water Supply Scheme |  |  | BILL/01514/2023-2024 | BP-2023-24-118 | 29/02/2024 | 29/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.76 | 0 | 0 | 0
5 | BANKURA | Sonamukhi | Bankura Division | Bhat Pushkarini Piped Water Supply Scheme | SM/12416 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR BHAT PUSHKARANI PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000373/2023-2024 | 2035/BQA | 24/07/2023 | 01/04/2026 | DEBAKI RANJAN SARKAR | 573.53 | 248.99 | 43.41 | 70
Total | [13 empty] | 793.25 | 269.98 | 34.03