## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Sonamukhi | Bankura Mechanical | Mathurabati Piped Water Supply Scheme | SM/12417 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk TW No-I & T/W No-II of Mathurabati piped water supply scheme under Bankura Mechanical Division, PHE Dte Block : Sonamukhi, Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000162/2023-2024 | 874/BMD | 04/05/2023 | 31/10/2023 | ABHIJIT MUKHERJEE | 35.79 | 15.18 | 42.43 | 43
2 | BANKURA | Sonamukhi | Bankura Division | Mathurabati Piped Water Supply Scheme | SM/12417 | New | Material Requisition To Resource Division |  |  | RTOR000058/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 55.63 | 0 | 0 | 0
3 | BANKURA | Sonamukhi | Bankura Division | Mathurabati Piped Water Supply Scheme | SM/12417 | New | Material Requisition To Resource Division |  |  | RTOR000012/2024-2025 | 2011/BQA | 26/07/2024 | 26/07/2024 | Resource Division | 6.17 | 0 | 0 | 0
4 | BANKURA | Sonamukhi | Bankura Mechanical | Mathurabati Piped Water Supply Scheme | SM/12417 | New | Shifting work of 11KV HT power line at Mathurabati HW site under B.M.D PHE Dte |  |  | BILL/01098/2024-2025 | BP-2024-25-255 | 25/10/2024 | 25/10/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.38 | 0 | 0 | 0
5 | BANKURA | Sonamukhi | Bankura Mechanical | Mathurabati Piped Water Supply Scheme | SM/12417 | New | New Service Connection for MATHURABATI (JL NO-70,PLOT-2)Water supply scheme under Bankura Mechanical Division PHE DTE |  |  | BILL/00023/2024-2025 | BP-2024-25-102 | 21/06/2024 | 21/06/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.82 | 0 | 0 | 0
6 | BANKURA | Sonamukhi | Bankura Mechanical | Mathurabati Piped Water Supply Scheme | SM/12417 | New | Mathurabati Piped Water Supply Scheme |  |  | BILL/01518/2023-2024 | BP-2023-24-117 | 29/02/2024 | 29/02/2024 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0 | 0
7 | BANKURA | Sonamukhi | Bankura Division | Mathurabati Piped Water Supply Scheme | SM/12417 | New | Instalation of scheme information board for 2 nos. sites of Mathurabati Piped Water Supply Scheme (SM/12417) & 4 nos. sites of Pathara Piped Water Supply Scheme (SM/14009) within Sonamukhi Block under Bishnupur Sub-Division of Bankura Division, PHE Dte. | Assistant Engineer | Junior Engineer | ORD/001892/2024-2025 | 570/VSD | 27/09/2024 | 12/10/2024 | PARTHA ROY | 0.9 | 0 | 0 | 0
8 | BANKURA | Sonamukhi | Bankura Division | Mathurabati Piped Water Supply Scheme | SM/12417 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR MATHURABATI PIPED WATER SUPPLY SCHEME, BLOCK- SONAMUKHI, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000106/2023-2024 | 1189/BQA | 22/05/2023 | 22/02/2024 | PARTHA PRATIM CHHATAIT | 422.56 | 27.61 | 6.53 | 65
Total | [13 empty] | 532.37 | 42.79 | 8.04