## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BANKURA | Jaypur | Bankura Division | Harinashuli Piped Water Supply Scheme | SM/12422 | New | SOIL INVESTIGATION FOR 15 NOS PIPED WATER SUPPLY SCHEME OF DIFERENT PLACES UNDER JJM WITH IN JOYPUR BLOCK OF BANKURA DISTRICT UNDER BANKURA DIVISION, PHE DTE. | Assistant Engineer | Junior Engineer | ORD/000413/2022-2023 | 351/BQA | 21/02/2023 | 23/03/2023 | MABCO CONSULTANT | 15.12 | 1.08 | 7.14 | 30
2 | BANKURA | Jaypur | Bankura Division | Harinashuli Piped Water Supply Scheme | SM/12422 | New | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 79BQA | 06/01/2023 | 06/01/2023 | Resource Division | 118.81 | 0 | 0 | 0
3 | BANKURA | Jaypur | Bankura Division | Harinashuli Piped Water Supply Scheme | SM/12422 | New | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 2522/BQA | 08/09/2023 | 08/09/2023 | Resource Division | 14.41 | 0 | 0 | 0
4 | BANKURA | Jaypur | Bankura Mechanical | Harinashuli Piped Water Supply Scheme | SM/12422 | New | Acceptance cum Formal work order for the work of Providing, installation of Pumping machineries with other electro-mechanical accessories for newly sunk at TW No-I & T.W No-II of Harinashuli piped water supply scheme Block : Joypur under Bankura Mechanical Division, PHE Dte. Dist: Bankura. | Assistant Engineer | Junior Engineer | ORD/000164/2023-2024 | 876/BMD | 04/05/2023 | 31/10/2023 | MITRA ENTERPRISE | 39.3 | 23.71 | 60.32 | 50
5 | BANKURA | Jaypur | Bankura Division | Harinashuli Piped Water Supply Scheme | SM/12422 | New | Jack Pussing, Land development & Rock cutting for foundation of 500 M3 capacity RCC OHR with 20 Mtr. staging height of Jadabnagar Water Supply Scheme & 450 M3 capacity RCC OHR with 20 Mtr. staging height of Harinasuli Water Supply Scheme under Bishnupur Sub Division of Bankura Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer | ORD/000869/2023-2024 | 3001/BQA | 03/11/2023 | 18/12/2023 | GOPAL CHANDRA CHOWDHURY | 74.67 | 36.64 | 49.07 | 95
6 | BANKURA | Jaypur | Bankura Mechanical | Harinashuli Piped Water Supply Scheme | SM/12422 | New | Harinsuli T/W-I |  |  | BILL/00846/2023-2024 | BP-2023-24-46 | 18/12/2023 | 18/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.01 | 0 | 0 | 0
7 | BANKURA | Jaypur | Bankura Mechanical | Harinashuli Piped Water Supply Scheme | SM/12422 | New | Harinasuli T/W-II |  |  | BILL/00847/2023-2024 | BP-2023-24-47 | 18/12/2023 | 18/12/2023 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.23 | 0 | 0 | 0
8 | BANKURA | Jaypur | Bankura Division | Harinashuli Piped Water Supply Scheme | SM/12422 | New | SUPPLY, DELIVERY, CONSTRUCTION, COMMISSIONING AND COMPLETION OF ALL CIVIL WORKS INCLUDING ALL ALLIED, RELATED AND ENABLING WORKS FOR HARINASHULI & JADABNAGAR PIPED WATER SUPPLY SCHEME, BLOCK- JOYPUR, DIST- BANKURA UNDER JJM INCLUDING TRIAL RUN FOR 3 MONTHS AND O&M FOR A PERIOD OF 3 YEARS UNDER BANKURA DIVISION,PHE Dte. | Assistant Engineer | Junior Engineer | ORD/000301/2023-2024 | 1918/BQA | 13/07/2023 | 30/09/2025 | GOPAL CHANDRA CHOWDHURY | 1591.82 | 547.66 | 34.4 | 85
Total | [13 empty] | 1862.38 | 609.09 | 32.7